## Summary Result
KRA-1
KRA | KPI Measure | How To Measure | Target | Weight
Adherence to assigned project as per timeline | % Achievement | (No. of task completed as timeline vs Total no. of projects) x 100 | 100% | 30
| Tasks Assigned | Tasks Fnished | Started on Time | Finished onTime
| 90 | 90 | 88 | 89
|  |  | Total Score | 98.88

## Assign Activity as per timeline
Project Title | Project Details | Milestone | Activity | Task | Plan Start Date | Actual Start Date | Start On Time | Plan End Date | Actual End Date | Finish On Time | Assign Person HR ID | Assign Person Name
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Process and UI | Oracle Process | Draw and overview of Receivable process | 2020-09-13 | 2020-09-14 | 0 | 2020-09-16 | 2020-09-16 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Process and UI | Oracle Process | Take screenshotts of major process in Oracle | 2020-09-17 | 2020-09-17 | 1 | 2020-09-20 | 2020-09-20 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Process and UI | iBMS Delivery Process | Take screenshots of OMR system | 2020-09-21 | 2020-09-21 | 1 | 2020-09-22 | 2020-09-22 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Process and UI | iBMS Delivery Process | Write short notes on each UI and find respective APIs | 2020-09-23 | 2020-09-23 | 1 | 2020-09-28 | 2020-09-28 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Process and UI | iBMS Delivery Process | Find out the package and procedures for each UI | 2020-09-29 | 2020-09-28 | 1 | 2020-10-05 | 2020-10-05 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Tuning | Performance Tuning | Calculate each query time | 2020-10-05 | 2020-10-05 | 1 | 2020-10-30 | 2020-10-30 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Documentation | TDD | Prepare TDD | 2020-11-01 | 2020-11-01 | 1 | 2020-11-07 | 2020-11-07 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Documentation | Commenting | Source code commenting | 2020-11-08 | 2020-11-08 | 1 | 2020-11-15 | 2020-11-15 | 1 | 17020000012681 | Tonmoy Rudra
OMR (Application,AIT,VAT,CDW,LPC) system performance tuning, detailed documentation on business process, and source code. Code review and commenting on OMR software. Mr. Tonmoy is working it. | OMR (Application, CDW, LPC, AIT) system performance tuning, business process documentation, and code documentation. Application operating style change and code commenting. | Developments | Schedular based process | Schedular based process and smart UI | 2020-11-01 | 2020-11-01 | 1 | 2020-11-30 | 2020-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Authentication | Authentication | Login table creatation | 2020-10-22 | 2020-10-22 | 1 | 2020-10-22 | 2020-10-22 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Authentication | Authentication | API endpoint for login. | 2020-10-22 | 2020-10-22 | 1 | 2020-10-22 | 2020-10-22 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Business Units | Business Unit table Creation | 2020-10-24 | 2020-10-24 | 1 | 2020-10-24 | 2020-10-24 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Business Units | API endpoint for Business Units. | 2020-10-24 | 2020-10-24 | 1 | 2020-10-24 | 2020-10-22 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Department | Department table Creation | 2020-10-24 | 2020-10-24 | 1 | 2020-10-24 | 2020-10-22 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Department | API endpoint for Department. | 2020-10-25 | 2020-10-25 | 1 | 2020-10-25 | 2020-10-25 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Divisions | Divisions table Creation | 2020-10-25 | 2020-10-25 | 1 | 2020-10-25 | 2020-10-25 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Divisions | API endpoint for Divisions. | 2020-10-25 | 2020-10-25 | 1 | 2020-10-25 | 2020-10-25 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Job Classifications | Job Classifications table Creation | 2020-10-27 | 2020-10-27 | 1 | 2020-10-27 | 2020-10-27 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Job Classifications | API endpoint for Job Classifications | 2020-10-27 | 2020-10-27 | 1 | 2020-10-27 | 2020-10-27 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Job Functions | Job Functions table Creation | 2020-10-27 | 2020-10-27 | 1 | 2020-10-27 | 2020-10-27 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Job Functions | API endpoint for Job Functions. | 2020-10-27 | 2020-10-27 | 1 | 2020-10-27 | 2020-10-27 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Legal Entities | Legal Entities table Creation | 2020-10-28 | 2020-10-28 | 1 | 2020-10-28 | 2020-10-28 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Legal Entities | API endpoint for Legal Entities. | 2020-10-28 | 2020-10-28 | 1 | 2020-10-28 | 2020-10-28 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Positions | Positions table Creation | 2020-10-28 | 2020-10-28 | 1 | 2020-10-28 | 2020-10-28 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Positions | API endpoint for Positions. | 2020-10-28 | 2020-10-28 | 1 | 2020-10-28 | 2020-10-28 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Docker Instance | Install | Install Docker Desktop for windows Machine | 2020-11-23 | 2020-11-23 | 1 | 2020-11-24 | 2020-11-24 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Docker Instance | Create | Create Docker Instance for Elasticsearch from Comopse yml file | 2020-11-25 | 2020-11-25 | 1 | 2020-11-26 | 2020-11-26 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Docker Instance | Create | Create Docker Instance for Kibana from Comopse yml file | 2020-11-29 | 2020-11-29 | 1 | 2020-11-30 | 2020-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Docker Instance | Run and check | Verify that Elasticsearch and Kivana is up and running | 2020-11-29 | 2020-11-29 | 1 | 2020-11-30 | 2020-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Serilog | Serilog Install | Install Serilog package and other | 2020-12-01 | 2020-12-01 | 1 | 2020-12-03 | 2020-12-03 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Serilog | Add Serilog | Add serilog in appsetting.json file | 2020-12-01 | 2020-12-01 | 1 | 2020-12-03 | 2020-12-03 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Serilog | Configure Logging | Configuring Logging in Program.cs | 2020-12-01 | 2020-12-01 | 1 | 2020-12-03 | 2020-12-03 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Kibana | Create Index | Create an index pattern in Kibana to show data with @timestamp field | 2020-12-05 | 2020-12-05 | 1 | 2020-12-06 | 2020-12-06 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Kibana | Filter | Filter data by Logging level, time, and other | 2020-12-05 | 2020-12-05 | 1 | 2020-12-06 | 2020-12-06 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Logging | Offline Logging | Offline logging when kibana server is not working, and when server is back then write those log in elasticsearch | 2020-12-05 | 2020-12-05 | 1 | 2020-12-06 | 2020-12-06 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Please include secure logging in SAP CPI project. We want to track all logins including failures. Runtime error logs and unauthorized attempts to access API endpoints should be there. | Tracking the web request and track hacking attempts. Also track the runtime error of WebAPIs. | Logging | Logging Contant | Logging all kind of log level (ex. error, information, success, warning, debug) on | 2020-12-07 | 2020-12-07 | 1 | 2020-12-13 | 2020-12-13 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | DB Design | DB Design | DB design for IntroLtr_EmployeeDataMaster | 2020-12-30 | 2020-12-30 | 1 | 2020-12-30 | 2020-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | DB Design | DB Design | DB design for IntroLtr_SalaryDetails and load it on Project | 2020-12-30 | 2020-12-30 | 1 | 2020-12-30 | 2020-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Get All employee list by fileloacationbased and userid | 2020-12-31 | 2020-12-31 | 1 | 2021-01-02 | 2021-01-02 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Get that employee information and place of posting address | 2020-12-31 | 2020-12-31 | 1 | 2021-01-02 | 2021-01-02 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Get last month salary information as like: Gross, Deduction etc. | 2020-12-31 | 2020-12-31 | 1 | 2021-01-02 | 2021-01-02 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Save all leatest information for salary report as like employee information and salary addition and deduction | 2021-01-03 | 2021-01-03 | 1 | 2021-01-03 | 2021-01-03 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Genarate RDLC report and response a blob file | 2021-01-03 | 2021-01-03 | 1 | 2021-01-05 | 2021-01-05 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | API | Web API | Get report data by ref ID | 2021-01-05 | 2021-01-05 | 1 | 2021-01-06 | 2021-01-06 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | UI | Angular UI | Menu Management, User Management, | 2021-01-07 | 2021-01-07 | 1 | 2021-01-07 | 2021-01-07 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | UI | Angular UI | Intregate all GET and POST API | 2021-01-10 | 2021-01-10 | 1 | 2021-01-10 | 2021-01-10 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | UI | Angular UI | User add/remove custom addition and deduction payitem and calculate total and total take home. | 2021-01-10 | 2021-01-10 | 1 | 2021-01-12 | 2021-01-12 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | UI | Angular UI | Save all leatest data and Genarate report from blob data | 2021-01-12 | 2021-01-12 | 1 | 2021-01-12 | 2021-01-12 | 1 | 17020000012681 | Tonmoy Rudra
Dear Saiful bhai, as per attached format please, prepare a salary certificate in ibms software. | Employee self-service salary certificate request and issued by respective finance personal with maintaining proper authenticity. | UI | Angular UI | Show report data by RefID | 2021-01-12 | 2021-01-12 | 1 | 2021-01-13 | 2021-01-13 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Employee | Create Employee Model On Database | 2021-02-01 | 2021-02-01 | 1 | 2021-02-23 | 2021-02-23 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Documentation | API Documentation | API Documantation from JSON | 2021-05-15 | 2021-03-09 | 1 | 2021-05-31 | 2021-03-11 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Documentation | API Documentation | POST man Collection | 2021-05-15 | 2021-03-15 | 1 | 2021-05-31 | 2021-03-16 | 1 | 17020000012681 | Tonmoy Rudra
Request for MR application history in OMR report. | Self monitoring toools to manage wrong and MR Over application. In addition auto diagnosis of the application and respective notification to the stakeholder | Application History | Application History | Application History | 2021-04-05 | 2021-03-01 | 1 | 2021-04-07 | 2021-03-04 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Data Merge | Write StoreProcedure for 6 table data Dump from SAP_CPI_Integration_DB to dbIBMS develop | 2021-03-18 | 2021-03-18 | 1 | 2021-03-23 | 2021-03-23 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Data Merge | Write StoreProcedure for 1 table data Dump from SAP_CPI_Integration_DB to dbIBMS develop sap_emloyee to hr_employees | 2021-03-23 | 2021-03-23 | 1 | 2021-03-31 | 2021-03-31 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Foundation Object | Data Merge | Create 6 New table on dbIBMS as like Sap database. hr_businessUnit > sap_BusinessUnit, hr_fuction > sap_division, hr_subFunction > sap_department, hr_area > sap_area, hr_subArea > sap_subArea, hr_support > sap_support, | 2021-03-18 | 2021-03-18 | 1 | 2021-03-21 | 2021-03-21 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Hire/Rehire | Create a procedure for data merge from SAP table to dbIBMS table | 2021-03-25 | 2021-03-25 | 1 | 2021-03-28 | 2021-03-28 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Promotion | Create a procedure for data merge from SAP table to dbIBMS table | 2021-03-29 | 2021-03-29 | 1 | 2021-03-31 | 2021-03-31 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Transfer | Create a procedure for data merge from SAP table to dbIBMS table | 2021-04-01 | 2021-04-01 | 1 | 2021-04-04 | 2021-04-04 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Upgradation | Create a procedure for data merge from SAP table to dbIBMS table | 2021-04-04 | 2021-04-01 | 1 | 2021-04-05 | 2021-04-04 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Data Change | Create a procedure for data merge from SAP table to dbIBMS table | 2021-04-06 | 2021-04-06 | 1 | 2021-04-07 | 2021-04-07 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Confirmation | Create a procedure for data merge from SAP table to dbIBMS table | 2021-04-08 | 2021-04-05 | 1 | 2021-04-10 | 2021-04-05 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Value Mapping | Update data for Company on Bm_CompanyBranch code-company = sap_code. Match manually by company name | 2021-04-11 | 2021-03-23 | 1 | 2021-04-11 | 2021-03-23 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Value Mapping | Update data for Location on BM_GeneralSetupUsers code-Location = sap_code, which is matching manually by location= ItemName | 2021-04-11 | 2021-03-23 | 1 | 2021-04-11 | 2021-03-23 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Value Mapping | Insert Data for Business Unit = hr_BusinessUnit Function = hr_function, subFunction = hr_subFunction, Area Code = hr_area, SubAreaCode, = hr_SubArea, Support Code =hr_Support, | 2021-04-12 | 2021-04-07 | 1 | 2021-04-15 | 2021-04-10 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Employee | Discussion Going On and continues development | 2020-11-01 | 2020-11-01 | 1 | 2021-03-15 | 2021-03-15 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Employee | Create controller and API for GET,POST, PUT, DELETE | 2021-03-04 | 2021-03-03 | 1 | 2021-03-10 | 2021-03-10 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Documentation | UAT | Check with SAP data is everything is working fine or not. | 2021-04-15 | 2021-04-10 | 1 | 2021-04-30 | 2021-04-10 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | UAT | Testing with SAP Team | Check with SAP data is everything is working fine or not. | 2021-04-15 | 2021-04-10 | 1 | 2021-04-30 | 2021-04-30 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Upgradation | Suspension for an employee | 2021-04-13 | 2021-04-13 | 1 | 2021-04-14 | 2021-04-13 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Leave | Leave implementation | 2021-05-09 | 2021-05-09 | 1 | 2021-05-11 | 2021-05-11 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Documentation | API Documentation | test 2 for pmt approval | 2021-06-01 | 2021-06-03 | 0 | 2021-06-16 | Null | 0 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Documentation | Test | Test 2 | 2021-05-27 | 2021-05-20 | 1 | 2021-05-31 | 2021-05-30 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Leave Integration | API Development | 2021-05-25 | 2021-05-25 | 1 | 2021-05-26 | 2021-05-26 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Leave Integration | Leave transfer to HRIS | 2021-06-07 | 2021-06-07 | 1 | 2021-06-10 | 2021-06-10 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Family Integration | API Development | 2021-05-31 | 2021-05-31 | 1 | 2021-06-02 | 2021-06-02 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Family Integration | Family Transfer to HRIS | 2021-06-07 | 2021-06-07 | 1 | 2021-06-10 | 2021-06-10 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Salary Integration | API Development | 2021-06-13 | 2021-06-13 | 1 | 2021-06-14 | 2021-06-14 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Backup Plan | Salary Integration | Salary Transfer to HRIS | 2021-06-15 | 2021-06-15 | 1 | 2021-06-20 | 2021-06-20 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | UAT | QA | DB Cloning | 2021-06-08 | 2021-06-08 | 1 | 2021-06-09 | 2021-06-09 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | UAT | QA | New host for QA API connection with QA DB | 2021-06-08 | 2021-06-08 | 1 | 2021-06-09 | 2021-06-09 | 1 | 17020000012681 | Tonmoy Rudra
Tonmoy, Create a basic structure of WebAPI for the CPI integration. We need to finalize the transfer procedure later. Keep in mind that models can be changed anytime. So develop the project in such a way that we can incorporate the changes with a minimum change in code. | Developing WebAPIs to comeplete the integration between SAP SuccessFactors and BSRM on-premise applications. SAP CPI is a cloud based application which will send data to our WebAPIs. This development will be as per EY's recommendation and field to field mapping with SAP SF. | Employee Object | Employee | Add Bank Id and bank account number on employee model + data Mapping with transfer | 2021-06-20 | 2021-06-19 | 1 | 2021-06-27 | 2021-06-27 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Authentication | UI | Login UI | 2021-06-17 | 2021-06-17 | 1 | 2021-06-19 | 2021-06-19 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Authentication | API Integration | Login with HRIS Credential | 2021-06-17 | 2021-06-17 | 1 | 2021-06-19 | 2021-06-19 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Dashboard | Dashboard view | A Simple and good looking dashboard view with Data | 2021-06-20 | 2021-06-20 | 1 | 2021-06-24 | 2021-06-24 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Dashboard | Dashboard view | Show data to click board box | 2021-06-20 | 2021-06-20 | 1 | 2021-06-24 | 2021-06-24 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Dashboard | Dashboard view | Date wise Filter | 2021-06-20 | 2021-06-20 | 1 | 2021-06-24 | 2021-06-24 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Dashboard | Chart View | Reason wise chart view | 2021-06-20 | 2021-06-20 | 1 | 2021-06-24 | 2021-06-24 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Project List | Advance search | Advance Search with different type filter | 2021-06-27 | 2021-06-27 | 1 | 2021-06-30 | 2021-06-30 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Details page | Show project details | Project Details show | 2021-06-27 | 2021-06-27 | 1 | 2021-06-30 | 2021-06-30 | 1 | 17020000012681 | Tonmoy Rudra