## Summary Result
KRA-5
KRA | KPI Measure | How To Measure | Target | Weight
Develop 1 new project as Project Lead | % Achievement |  | 100% | 25
Sr | Project Name | Target date | Finished date
1 | Introductory letter | 15-Jan-2021 | 13-Jan-2021
|  | Total Point | 100

## Plan Sheet
CRNumber | Milestone | Activity | Task | PlanStartDate | PlanEndDate | Users
HRIS-PAYSLP-1 | DB Design | DB Design | DB design for IntroLtr_EmployeeDataMaster | 30-Dec-2020 | 30-Dec-2020 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | DB Design | DB Design | DB design for IntroLtr_SalaryDetails and load it on Project | 30-Dec-2020 | 30-Dec-2020 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Get All employee list by fileloacationbased and userid | 31-Dec-2020 | 02-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Get that employee information and place of posting address | 31-Dec-2020 | 02-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Get last month salary information as like: Gross, Deduction etc. | 31-Dec-2020 | 02-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Save all leatest information for salary report as like employee information and salary addition and deduction | 03-Jan-2021 | 03-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Genarate RDLC report and response a blob file | 03-Jan-2021 | 05-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | API | Web API | Get report data by ref ID | 05-Jan-2021 | 06-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | UI | Angular UI | Menu Management, User Management, | 07-Jan-2021 | 07-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | UI | Angular UI | Intregate all GET and POST API | 10-Jan-2021 | 10-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | UI | Angular UI | User add/remove custom addition and deduction payitem and calculate total and total take home. | 10-Jan-2021 | 12-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | UI | Angular UI | Save all leatest data and Genarate report from blob data | 12-Jan-2021 | 12-Jan-2021 | tonmoy.rudra@bsrm.com
HRIS-PAYSLP-1 | UI | Angular UI | Show report data by RefID | 12-Jan-2021 | 13-Jan-2021 | tonmoy.rudra@bsrm.com