## result
KRA-1
KRA | KPI Measure | How To Measure | Target | Weight
Adherence to assigned project as per timeline | % Achievement | (No. of projects completed as timeline vs Total no. of projects) x 100 | 100% | 25
| Tasks Assigned | Tasks Fnished | Started on Time | Finished onTime
| 82 | 82 | 82 | 80 | 97.561

## Tonmoy
Project Title | Project Details | Milestone | Activity | Task | Plan Start Date | Actual Start Date | Start On Time | Plan End Date | Actual End Date | Finish On Time | Assign Person HR ID | Assign Person Name
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Authentication | UI | Login UI | 2021-07-01 | 2021-07-01 | 1 | 2021-07-03 | 2021-07-03 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Authentication | API Integration | Login with HRIS Credential | 2021-07-01 | 2021-07-01 | 1 | 2021-07-03 | 2021-07-03 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Dashboard | Dashboard view for Work list | A Simple and good looking dashboard view. | 2021-07-04 | 2021-07-01 | 1 | 2021-07-12 | 2021-07-11 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Dashboard | Worklist type load | Call PendingWorklistType get api | 2021-07-04 | 2021-07-04 | 1 | 2021-07-12 | 2021-07-11 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Dashboard | Worklist load | Load all work list | 2021-07-04 | 2021-07-04 | 1 | 2021-07-12 | 2021-07-11 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Details Page | Show Worklist Details | Worklist details Show | 2021-07-04 | 2021-07-04 | 1 | 2021-07-12 | 2021-07-11 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Approval | Approve | Approve | 2021-07-11 | 2021-07-11 | 1 | 2021-07-14 | 2021-07-11 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | Approval | Reject | Reject | 2021-07-11 | 2021-07-11 | 1 | 2021-07-14 | 2021-07-14 | 1 | 17020000012681 | Tonmoy Rudra
Please develop a web based system for COO sir, so that he can approve all HRIS and ERP approval from his mobile. Kindly develop by 15th July 2021. | Developing BMS for Web platform for better User Experince with Responsive UI | UAT | UAT | UAT | 2021-07-12 | 2021-07-12 | 1 | 2021-07-14 | 2021-07-14 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | Comment | Add Comments | User add their comments on this system | 2021-07-01 | 2021-07-01 | 1 | 2021-07-10 | 2021-07-10 | 1 | 17020000012681 | Tonmoy Rudra
Create a web version of Lead Management. Senior management will use this portal to view the dashboard, summary, and details of a project. They will also be able to comments on any project. | To Develop a System where user can see all of his and hir downline details data with a Dashboard View | UAT | UAT | UAT | 2021-07-11 | 2021-07-11 | 1 | 2021-07-14 | 2021-07-14 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Create a Web api Structure on ASP.Net Core | 2021-07-28 | 2021-07-28 | 1 | 2021-07-29 | 2021-07-29 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Load DB Model | 2021-07-29 | 2021-07-29 | 1 | 2021-07-31 | 2021-07-31 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Create Controller , Repository, Model for Create Order | 2021-08-01 | 2021-08-01 | 1 | 2021-08-05 | 2021-08-05 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Create Controller , Repository, Model for Confirm Delivery | 2021-08-01 | 2021-08-01 | 1 | 2021-08-05 | 2021-08-05 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Create Controller , Repository, Model for Verify | 2021-08-01 | 2021-08-01 | 1 | 2021-08-05 | 2021-08-05 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Create Controller , Repository, Model for CC Problem Controller | 2021-08-08 | 2021-08-08 | 1 | 2021-08-09 | 2021-08-09 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Send mail and Send SMS Cofiguration | 2021-08-08 | 2021-08-08 | 1 | 2021-08-09 | 2021-08-09 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | API | Create API | Add CORS, Swagger, and other | 2021-08-08 | 2021-08-08 | 1 | 2021-08-09 | 2021-08-09 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | Web UI | Modify Angular | Modify angular 6 project to Angular 11 and related all module change | 2021-08-10 | 2021-08-09 | 1 | 2021-08-11 | 2021-08-10 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | Web UI | HTTP Service | Change all HTTP service to HTTP Client | 2021-08-10 | 2021-08-09 | 1 | 2021-08-11 | 2021-08-10 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | Web UI | Modify Other and Issue Fixing | Modify Other Module and fixing all issue | 2021-08-12 | 2021-08-12 | 1 | 2021-08-15 | 2021-08-14 | 1 | 17020000012681 | Tonmoy Rudra
Need an API to incorporate with the new BSRM Wires Website for BSRM Sheba. | BSRM IT is developing interfaces for BSRM Corporate website developer so that internal application can receive data from corporate website | UAT | UAT | Testing and Build | 2021-08-16 | 2021-08-16 | 1 | 2021-08-16 | 2021-08-16 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Application Architecture | Web API | Create API project with EF Core, and basic setup. | 2022-03-07 | 2022-03-06 | 1 | 2022-03-08 | 2022-03-08 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Application Architecture | Web API | Authentication and Authorization | 2022-03-09 | 2022-03-09 | 1 | 2022-03-10 | 2022-03-10 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Application Architecture | Angular UI | Create Project, Login Screen, Dashboard, Menu. | 2022-03-12 | 2022-03-12 | 1 | 2022-03-14 | 2022-03-13 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Nature Of Accounts Setup | NoA assignment, | 2022-06-14 | 2022-06-14 | 1 | 2022-06-15 | 2022-06-15 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Nature Of Accounts Setup | NoA hirerchy | 2022-06-19 | 2022-06-19 | 1 | 2022-06-20 | 2022-06-20 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | File template management | File template download as per NoA assignment | 2022-06-27 | 2022-06-27 | 1 | 2022-06-29 | 2022-06-29 | 1 | 17020000012681 | Tonmoy Rudra
Implement the revised Credit Approval Hierarchy for Cash/ Immediate/ BG and LC (Version: 2) and Credit Hold Release Approval Hierarchy (Version: 2) in the ERP system | Implement the revised Credit Approval Policy considering Cash/Immediate, BG and LC and changes on Approval Hierarchy. In addition, resolve partical credit hold release issue. | Credit Hold 2021 Policy | implement new policy approval for Credit payment teram | implement new policy approval for Credit payment teram | 2022-06-01 | 2022-06-01 | 1 | 2022-06-01 | 2022-06-30 | 0 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Leave workflow change for K Rahaman In SF | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | On SF, In beneficiary dependent default value is no. It needs to Yes | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Rabbi is not getting compensation for Jungal. Please see this Issue URGENT | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | On SF, HR Admin Change Group for | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | ON SF, Change function head Group | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | On SF, Leave without pay (BASIC) is not deducted | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Org chart error and manage my team issue | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Please check the attached file and remove duplicate entry from iBMS. (Problem due to Auto data transfer from SAP_SF to iBMS). | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | For LMS, Upload Department details to the user in SF Development System. | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Please address the accessibility issue in the SAPSF. Rabbi can not perform any employees DATA change for Jungal Warehouse and Mymensingh Warehouse. Need to permission for | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | LMS | Add LMS Certificate design | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Workflow group change. | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | On Resignation workflow, add HRAdminGroup_DG as a contributor for Notification | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-12-30 | 0 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | On SF, please change the workflow group for HR ADMIN as per our communication. | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | ownership of employee file is not transferring to a target location when performing employee transfer from SF | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | The new job classification for Rajshahi. | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-01 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Can not create Sequence for Job Classification | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | LMS | Add Department permission on user LMS admin to Sap Development | 2021-10-01 | 2021-10-01 | 1 | 2021-10-30 | 2021-10-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Email Configuration | Leave | Generate Email notification with leave data for leave workflow Initiator, approver, rejector, generic format. | 2021-10-01 | 2021-10-01 | 1 | 2021-10-30 | 2021-10-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Email Configuration | Resignation | Generate Resignation Email notification with leave data for leave workflow. | 2021-10-01 | 2021-10-01 | 1 | 2021-10-30 | 2021-10-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | Report for Goal Management & Appraisal Data: Purpose - To know the condition of employees data input in PMGM goal setting , especially regarding “Achievement Lookup Table” setting. | 2022-01-10 | 2022-01-09 | 1 | 2022-02-28 | 2022-01-31 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | Report for Competency data of employees: Purpose - To identify the employees who don’t have assigned competency in the system, because we have detect some employees in the system where competency not visible in the goal setting form. | 2022-01-10 | 2022-01-09 | 1 | 2022-02-28 | 2022-01-31 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Support | PMGM | please support us to provide an user ID and password to read SAP Knowledge Base Article. We need these KBA to study problem and its resolution procedure related with PMGM. | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Support | EC | Success Factors to Compensation part for Nmgt. employees. Kindly provide me necessary access in Success Factors. | 2021-12-01 | 2021-12-01 | 1 | 2021-12-30 | 2021-12-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Support | EC | SF and IBMS separation date mismatch. Need to add +1 from SF to IBMS | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Support | Leave | On Leave application, hr time admin has not been received any CC notification | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Support | EC | On SF, Please change HR_admin permission for BSRM_Melting_1 from Modasser Ahmed to Imam Hossain as HR_Admin. | 2021-11-01 | 2021-11-01 | 1 | 2021-11-30 | 2021-11-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | HR Mashud vai inform me that MR. Asun shikder (Admin) can receive leave notifications emails for some employees. Check from which flow it will be sent. | 2022-01-24 | 2022-01-24 | 1 | 2022-01-25 | 2022-01-25 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We need PMGM admin permission to search/analyze and work on the PMGM issues in the production system as well as can describe the problems to you more effectively. For that provide some PMGM working area as sample according to your request. 1. Manage center of capabilities. 2. Manage templates 3. Email notification templates setting 4. Rating scales 5. Manage job profile content (not have edit button currently) 6. Manage job profile content import / Export | 2022-01-29 | 2022-01-29 | 1 | 2022-02-17 | 2022-02-12 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | New Joiner Email Notification Change. | 2022-01-23 | 2022-01-23 | 1 | 2022-02-28 | 2022-02-28 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | SAP Integration API Change - Sap Absence Comments range fixed for 4000 | 2022-02-08 | 2022-02-08 | 1 | 2022-02-08 | 2022-02-08 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Employee Education, Work Exp. template create for upload bulk upload. | 2022-01-25 | 2022-01-25 | 1 | 2022-03-31 | 2022-03-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | Dear Tonmoy Bhai, We need two report from PMGM module. I have attached sample format for these two report for your easy understanding. For any further clarification please let us know. [Ticket NO: 125233] | 2022-03-24 | 2022-03-24 | 1 | 2022-03-31 | 2022-03-31 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Add 2 New field for Position as per farooque bhai requirment. Position Holder ID, Position Holder Name. Note: Its need to be perform from Configure Business Menu [Ticket NO: 125260] | 2022-03-09 | 2022-03-09 | 1 | 2022-03-10 | 2022-03-10 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Add 1 New field on Job Classification: 'Role Type' with Picklist value 'Critical', 'Non-Critical'. [Ticket NO: 125268] | 2022-03-01 | 2022-03-01 | 1 | 2022-03-10 | 2022-03-09 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | HR Admin access is not working in SuccessFactor of Mohammad Imam Hossen for BSRM Steels Ltd. (Melting - 1), KOA- Mr. Suman Bhai/ Mr. Tanmoy Da. Ticket No: 127058 | 2022-04-07 | 2022-04-07 | 1 | 2022-04-07 | 2022-04-07 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Dear Tonmoy Bhai, We need two report from PMGM module. I have attached sample format for these two report for your easy understanding. For any further clarification please let us know. Ticket NO: 125233 | 2022-03-12 | 2022-03-12 | 1 | 2022-04-10 | 2022-04-10 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Dear Tonmoy Bhai, I am not able to work on any tab relating to me in production system. For example: Delete my form / launch form for me, etc. As discussed, please try to provide me PMGM admin permission / self permission to execute necessary workings. [Ticket NO: 124736] | 2022-03-15 | 2022-03-15 | 1 | 2022-05-31 | 2022-05-30 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | SuccessFactors (PMGM): Please Made the calibration field read-only in Manager’s page. Ticket Details [Ticket NO: 129354] | 2022-05-08 | 2022-05-08 | 1 | 2022-05-08 | 2022-05-08 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Please make available Professional competency in year end + 1 Manager view for Form A(+1) and B (+1). Ticket Details [Ticket NO: 129355] | 2022-05-08 | 2022-05-08 | 1 | 2022-05-09 | 2022-05-08 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Professional competency not showing in year end + 1 Manager view for Form A and B | 2022-05-09 | 2022-05-09 | 1 | 2022-05-10 | 2022-05-10 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing goals rating for form A | 2022-05-09 | 2022-05-09 | 1 | 2022-05-09 | 2022-05-09 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing goals rating for form B. Ticket Details [Ticket NO: 129359] | 2022-05-10 | 2022-05-10 | 1 | 2022-05-10 | 2022-05-10 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing goals rating for form A+1, Ticket Details [Ticket NO: 129360] | 2022-05-11 | 2022-05-11 | 1 | 2022-05-11 | 2022-05-11 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing goals rating for form B+1,Ticket Details [Ticket NO: 129361] | 2022-05-11 | 2022-05-11 | 1 | 2022-05-11 | 2022-05-11 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing competency rating for form A,Ticket Details [Ticket NO: 129362] | 2022-05-11 | 2022-05-11 | 1 | 2022-05-11 | 2022-05-11 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Not showing competency rating for form B,Ticket Details [Ticket NO: 129363] | 2022-05-11 | 2022-05-11 | 1 | 2022-05-11 | 2022-05-11 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Align field permission for Form A from Manage Templates,Ticket Details [Ticket NO: 129366] | 2022-05-12 | 2022-05-12 | 1 | 2022-05-12 | 2022-05-12 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Align field permission for Form B from Manage Templates,Ticket Details [Ticket NO: 129367] | 2022-05-12 | 2022-05-12 | 1 | 2022-05-12 | 2022-05-12 | 1 | 17020000012681 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | Align field permission for Form A+1 , B+1 from Manage Templates, Ticket Details [Ticket NO: 129368-129369] | 2022-05-12 | 2022-05-12 | 1 | 2022-05-12 | 2022-05-12 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Budget Initiate | PBCPM team initiate budget | 2022-06-08 | 2022-06-08 | 1 | 2022-06-12 | 2022-06-12 | 1 | 17020000012681 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Calendar Setup | Calender setup with Add, edit, update, delete | 2022-05-29 | 2022-05-29 | 1 | 2022-05-30 | 2022-05-30 | 1 | 17020000012681 | Tonmoy Rudra