## Result
KRA-1
KRA | KPI Measure | How To Measure | Target | Weight
Adherence to assigned project as per timeline | % Achievement | (No. of project task as per timeline vs. Total no. of Project task) x 100 | 100% | 30
| Tasks Assigned | Tasks Fnished | Started on Time | Finished onTime
| 91 | 90 | 89 | 90 | 98.9011
Rating | Target Level | Rating Description
1 | 80
2 | 85
3 | 90
4 | 95
5 | 100

## Tonmoy Task Data
Project Title | Project Details | Milestone | Activity | Task | Task ID | Plan Start Date | Actual Start Date | Start On Time | Plan End Date | Actual End Date | Finish On Time | Assign Person HR ID | Assign Person Name
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | Prepare ERD | 4131 | 2023-05-10 | 2023-05-10 | 1 | 2023-05-11 | 2023-05-11 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | New DB Object | 4132 | 2023-05-14 | 2023-05-14 | 1 | 2023-05-15 | 2023-05-15 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | API | Create API Structure with CQRS Pattern | 4133 | 2023-05-16 | 2023-05-16 | 1 | 2023-05-17 | 2023-05-17 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | UI | Angular Project setup + Login | 4134 | 2023-05-18 | 2023-05-18 | 1 | 2023-05-20 | 2023-05-20 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Authorization Setup | Preparer Setup | Setup for roster preparer From IBMS | 4135 | 2023-05-21 | 2023-05-21 | 1 | 2023-05-22 | 2023-05-22 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Show the roster workflow | 4136 | 2023-05-23 | 2023-05-23 | 1 | 2023-05-28 | 2023-05-28 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Prepare pattern data | 4137 | 2023-05-29 | 2023-05-29 | 1 | 2023-05-30 | 2023-05-30 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration-Bulk(Backend) | 4138 | 2023-05-31 | 2023-05-31 | 1 | 2023-06-01 | 2023-06-01 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration | 4139 | 2023-06-03 | 2023-06-03 | 1 | 2023-06-06 | 2023-06-06 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Generate sample data for 1 month | 4140 | 2023-06-07 | 2023-06-07 | 1 | 2023-06-14 | 2023-06-14 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Front end validation with Click validate button and show error | 4141 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-18 | 2023-06-18 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Back end validation | 4142 | 2023-06-19 | 2023-06-19 | 1 | 2023-06-21 | 2023-06-21 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Submission of prepared roster | 4143 | 2023-06-22 | 2023-06-22 | 1 | 2023-06-26 | 2023-06-26 | 1 | 17020000014498 | Tonmoy Rudra
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Concurrent Manager Desktop | Concurrent Manager Project | Create Concurrent for CSV File Upload | 3657 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | API | Create API to receive payroll data | 3615 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-22 | 2022-09-22 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | For Year end appraisal we need a report contains various rating. Sharing the format for your easy understanding. [Ticket NO: 133023] | 3329 | 2022-07-07 | 2022-07-07 | 1 | 2022-07-13 | 2022-07-13 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We have found error message when testing new goal plan 22-23 in the production system. Need to raise ticket to SAP. Please support us in this issue.. Ticket Details [Ticket NO: 136980] | 3510 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We need to update some features in the existing performance form (incorporate comments in +1 Manager, sign-off step) which was observed last year & discussed with you. Please support us in doing this in the system to start the new goal plan 22-23. Thank you Ticket Details [Ticket NO: 137115] | 3511 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-30 | 2022-09-30 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | As discussed, please upload bulk employees for proxy management. Ticket Details [Ticket NO: 139489] | 3571 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Add Proxy for HR person | 3572 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Develop | Develop classed to process CSV files | 3653 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | UI Design and Development | 3598 | 2022-12-26 | 2022-12-26 | 1 | 2023-01-02 | 2023-01-02 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Physical Inspection | 3599 | 2023-01-03 | 2023-01-03 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch details | 3600 | 2023-01-16 | 2023-01-16 | 1 | 2023-01-22 | 2023-01-22 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch correction | 3601 | 2023-01-23 | 2023-01-23 | 1 | 2023-01-30 | 2023-01-30 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Formula item configuration and modification | 3602 | 2023-01-31 | 2023-01-31 | 1 | 2023-02-02 | 2023-02-02 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Group Setup, Param Setup | 2596 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item type setup | 2597 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Ratio Setup | 2598 | 2022-09-13 | 2022-09-13 | 1 | 2022-09-15 | 2022-09-15 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Company Setup | 2599 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Setup | User and workflow and cost center and location setup, ADD Edit And delete | 2600 | 2022-08-10 | 2022-08-10 | 1 | 2022-08-12 | 2022-08-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Permissions Setup | Permission on ORG, Region, Common Budget, | 2601 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-14 | 2022-08-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Nature Of Accounts Setup | Common budget NoA setup, | 2603 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-17 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | PBCPM(Planing Budget….) Common Budget Setup | Common budget NoA setup, | 2605 | 2022-08-21 | 2022-08-21 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Sales Budget Setup with Region. | Region wise setup. | 2606 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Draft Mode Save | Draft mode save from file and UI. | 2609 | 2022-07-03 | 2022-07-03 | 1 | 2022-07-04 | 2022-07-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2610 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-21 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Submit Budget | Submit budget with validation and save | 2611 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Multi layer approval | 2612 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-25 | 2022-08-25 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | PBCPM Comments entry | 2613 | 2022-08-23 | 2022-08-02 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Notification Mail | 2614 | 2022-08-25 | 2022-08-25 | 1 | 2022-08-27 | 2022-08-27 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Work flow Stage visibility | 2615 | 2022-08-28 | 2022-08-28 | 1 | 2022-08-28 | 2022-08-28 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Draft Mode Save | Draft mode save from file and UI. | 2616 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2617 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-30 | 2022-08-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Submit Budget | Submit budget with validation and save | 2618 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Multi layer approval | 2619 | 2022-08-31 | 2022-08-31 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | PBCPM Comments entry | 2620 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-01 | 2022-09-01 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Notification Mail | 2621 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Work flow Stage visibility | 2622 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-05 | 2022-09-05 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | File template management | File template Upload as per NoA assignment | 2624 | 2022-09-06 | 2022-09-06 | 1 | 2022-09-06 | 2022-09-06 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Draft Mode Save | Draft mode save from file and UI. | 2625 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2626 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Submit Budget | Submit budget with validation and save | 2627 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Multi layer approval | 2628 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-11 | 2022-09-11 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | PBCPM Comments entry | 2629 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Notification Mail | 2630 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Work flow Stage visibility | 2631 | 2022-09-12 | 2022-09-11 | 1 | 2022-09-13 | 2022-09-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template download as per NoA assignment | 2632 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template Upload as per NoA assignment | 2633 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Draft Mode Save | Draft mode save from file and UI. | 2634 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2635 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Submit Budget | Submit budget with validation and save | 2636 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Multi layer approval | 2637 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | PBCPM Comments entry | 2638 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Notification Mail | 2639 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Work flow Stage visibility | 2640 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template download as per NoA assignment | 2650 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template Upload as per NoA assignment | 2651 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Draft Mode Save | Draft mode save from file and UI. | 2652 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2653 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Submit Budget | Submit budget with validation and save | 2654 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Multi layer approval | 2655 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | PBCPM Comments entry | 2656 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Notification Mail | 2657 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Work flow Stage visibility | 2658 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template download as per NoA assignment | 2659 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template Upload as per NoA assignment | 2660 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Draft Mode Save | Draft mode save from file and UI. | 2661 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2662 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Submit Budget | Submit budget with validation and save | 2663 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Multi layer approval | 2664 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | PBCPM Comments entry | 2665 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Notification Mail | 2666 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template download as per submitted capital budget | 2667 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template Upload as per submitted capital budget. | 2668 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Work flow Stage visibility | 2669 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Review for previous process | Transfar previous reviews data to half yearly review. | 2673 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-08 | 2022-09-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Open Budget period | Budget setup activty by PBCPM | 2674 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Actual consumption for current year. | Pop View for actual consumption | 2675 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Access wise query preparation. | 2681 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-14 | 2022-09-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget view API | 2682 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget View UI | 2683 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | UAT | UAT | UAT | 2690 | 2022-11-08 | NULL | 0 | 2022-11-10 | NULL | 0 | 17020000014498 | Tonmoy Rudra