## RESULT
PROJECT NAME | NO OF TEST CASES | PASSED TEST CASE | FAILED TEST CASE | PERCENTAGE ACHIEVED
Budgeting System | 57 | 51 | 6 | 89.4737
Level 3 Middleware | 18 | 14 | 2 | 77.7778
Concurrent Manager | 3 | 3 | 0 | 100
Success Factors Payrol Integration | 3 | 3 | 0 | 100
| 81 | 71 | 8 | 87.6543

## Budgeting System
Test Cases-Budgeting
Test Case ID | Test Description | Step Number | Step Description | Execution Date | Pass/ Fail? | Comments
TC 1 | Login | 1 | Login with HRIS Credantial | 15/02/2023 | Pass
TC 2 | Logout | 1 | Logout from System. | 15/02/2023 | Pass
TC 3 | User Assignment By PBCPM | 1 | Download User setting template | 15/02/2023 | Pass
|  | 2 | Modify Data and upload User Setting data | 15/02/2023 | Fail
|  | 3 | Check all uploaded data is Come Or Not | 15/02/2023 | Pass
|  | 4 | Add single user setting data. | 15/02/2023 | Pass
|  | 5 | Edit a single row data. | 15/02/2023 | Pass
|  | 6 | Delete a specific single row data | 15/02/2023 | Pass
|  | 7 | Change user setting approver flow with huge data. | 15/02/2023 | Pass
|  | 8 | Search or filter from list | 15/02/2023 | Pass
TC 4 | NOA Assigment for Exp. & Common Budget By PBCPM | 1 | Download template | 15/02/2023 | Pass
|  | 2 | Modify Data and upload all data | 15/02/2023 | Pass
|  | 3 | Check all uploaded data is Come Or Not on grid | 15/02/2023 | Pass
|  | 4 | Add single data. | 15/02/2023 | Pass
|  | 5 | Edit a single row data. | 15/02/2023 | Pass
|  | 6 | Delete a specific single row data | 15/02/2023 | Pass
|  | 7 | Search or filter from list | 15/02/2023 | Pass
TC 5 | Organization Setup By PBCPM | 1 | Download template | 15/02/2023 | Pass
|  | 2 | Modify Data and upload all data | 15/02/2023 | Pass
|  | 3 | Check all uploaded data is Come Or Not on grid | 15/02/2023 | Pass
|  | 4 | Add single data. | 15/02/2023 | Pass
|  | 5 | Edit a single row data. | 15/02/2023 | Fail
|  | 6 | Delete a specific single row data | 15/02/2023 | Pass
|  | 7 | Search or filter from list | 15/02/2023 | Pass
TC 6 | Calender Add By PBCPM | 1 | Get All Calender | 15/02/2023 | Pass
|  | 2 | Add New Location | 15/02/2023 | Pass
|  | 3 | Edit Calender | 15/02/2023 | Fail
|  | 4 | Delete Spesific Calender Data | 15/02/2023 | Pass
TC 7 | Common Budget Types By PBCPM | 1 | Get All Data | 15/02/2023 | Pass
|  | 2 | Add New | 15/02/2023 | Pass
|  | 3 | Edit Data | 15/02/2023 | Pass
|  | 4 | Delete Data | 15/02/2023 | Pass
TC 8 | Asset & Asset Category | 1 | Get All Data | 15/02/2023 | Pass
|  | 2 | Add New | 15/02/2023 | Pass
|  | 3 | Edit Data | 15/02/2023 | Pass
|  | 4 | Delete Data | 15/02/2023 | Pass
TC 9 | Store And Spare Budget Files By PBCPM | 1 | Download Template | 15/02/2023 | Pass
|  | 2 | Upload modified file. | 15/02/2023 | Pass
TC 10 | Initiate Budget By PBCPM | 1 | Intiate Budget with Send Mail | 15/02/2023 | Pass
|  | 2 | Intiate Budget without send mail | 15/02/2023 | Pass
TC 11 | Budget Preparation for all type BY Preprarer | 1 | Log In | 15/02/2023 | Pass
|  | 2 | Check budget list with type wise | 15/02/2023 | Pass
|  | 3 | Filter Budget list | 15/02/2023 | Pass
|  | 4 | Entry their budget | 15/02/2023 | Pass
|  | 5 | Draft Save | 15/02/2023 | Pass
|  | 6 | Edit and forward for approval | 15/02/2023 | Pass
|  | 7 | Rejected Budget edit and forward again for approval | 15/02/2023 | Pass
|  | 8 | Show Log. | 15/02/2023 | Pass
|  | 9 | Approval Flow Check | 15/02/2023 | Pass
TC 12 | Budget Approval By Approver | 1 | Log In | 15/02/2023 | Pass
|  | 2 | Check pending Budget waiting for approval | 15/02/2023 | Pass
|  | 3 | Reject Budget | 15/02/2023 | Fail
|  | 4 | Approve Budget | 15/02/2023 | Pass
|  | 5 | Status Update | 15/02/2023 | Pass
|  | 6 | Check PBCPM Activity | 15/02/2023 | Pass
TC 13 | Email Sent | 1 | Check mail for Initiate Budget | 15/02/2023 | Fail
|  | 2 | Check mail for Forward Budget to the approver. | 15/02/2023 | Pass
|  | 3 | Check mail for Send back or Reject Budget. | 15/02/2023 | Pass

## Level 3 Middleware
Test Cases- Level 3 Middleware For Melting 2
Test Case ID | Test Description | Step Number | Step Description | Execution Date | Pass/ Fail? | Comments
TC 1 | Login | 1 | Login with HRIS Credantial | 2023-06-12 | Pass
TC 2 | Logout | 1 | Logout from System. | 2023-06-12 | Pass
TC 3 | Master Setup | 1 | All Formula items are available as per FDD | 2023-06-12 | Pass
|  | 2 | Edit Formula item & Enable disable is working | 2023-06-12 | Pass
|  | 3 | Global Parameter is working | 2023-06-12 | Pass
TC 4 | Batch View | 1 | Batch list is showing with status | 2023-06-12 | Pass
|  | 2 | Searching & filters are working | 2023-06-12 | Fail
|  | 3 | Batch details view are showing all necessary info. | 2023-06-12 | Pass
|  | 4 | Billet data is showing properly | 2023-06-12 | Fail
TC 5 | Batch Process | 1 | Physical Inspection Form contans all necessary fields | 2023-06-12 | Pass
|  | 2 | Validation is working | 2023-06-12 | Pass
|  | 3 | Batch closed successfully when validation done | 2023-06-12 | Pass
|  | 4 | Check batch status in oracle ebs | 2023-06-12 | Pass
|  | 5 | All steps have been processed successfully in Oracle | 2023-06-12 | Fail
|  | 6 | Declaring fake batch is working | 2023-06-12 | Fail
TC 6 | Batch Edit | 1 | Edit is enabled when validation failed | 2023-06-12 | Pass
|  | 2 | Ingredients are editable and working properly | 2023-06-12 | Pass
|  | 3 | Batch re-process is working after validation pass | 2023-06-12 | Pass
|  | 4 | Failed batch can be processed from OracleEBS | 2023-06-12 | Pass

## SF Payroll Integration
Test Cases- Success Factors Payrol Integration
Test Case ID | Test Description | Step Number | Step Description | Execution Date | Pass/ Fail? | Comments
T01 | Pay Component Transfer SF to IBMS | 1 | Basic Salary Transfer successfully | 2022-01-10 | Pass
|  | 2 | All Other Allowance Transfer Successfully | 2022-01-10 | Pass
|  | 3 | Medical Allowance Successfully | 2022-01-10 | Pass

## Concurrent Manager
Test Cases- Concurrent Manager
Test Case ID | Test Description | Step Number | Step Description | Execution Date | Pass/ Fail? | Comments
T01 | Concurrent Manager | 1 | Upload Excle to HRIS. | 15/10/2022 | Pass
|  | 2 | Concurrent Request Schedular Run automatically | 15/10/2022 | Pass
|  | 3 | Update Attendance Data | 15/10/2022 | Pass