## Sheet1
Project Title | Project Details | Milestone | Activity | Task | Task ID | Plan Start Date | Actual Start Date | Start On Time | Plan End Date | Actual End Date | Finish On Time | Assign Person HR ID | Assign Person Name
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Generate Challan WPPF | Generate Challan | Generate Challan | 3208 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-20 | 2022-09-19 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | Upload acknowledge of return by user | Upload acknowledge of return by user | 3222 | 2022-10-19 | 2022-10-16 | 1 | 2022-10-19 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | View uploaded acknowledement by HR and Accounts | View uploaded acknowledement by HR and Accounts | 3223 | 2022-10-19 | 2022-10-06 | 1 | 2022-10-19 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Monthly Tax Summary | Process and Query Preparation | 3493 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-14 | 2022-09-14 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report 108 | Process and Query Preparation | 3496 | 2022-10-03 | 2022-10-03 | 1 | 2022-09-04 | 2022-10-04 | 0 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report Perquisite | Process and Query Preparation | 3499 | 2022-10-06 | 2022-10-06 | 1 | 2022-10-06 | 2022-10-06 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Tax Deduction Summary | Process and Query Preparation | 3502 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Batch Creation and Status Upgradation | 3582 | 2022-11-20 | 2022-11-20 | 1 | 2022-11-20 | 2022-11-20 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Ingredient (IF+LRF+CCM) Lot identification and material transaction | 3583 | 2022-11-21 | 2022-11-21 | 1 | 2022-11-23 | 2022-11-24 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | (IF+LRF+CCM) step API | 3584 | 2022-11-24 | 2022-11-24 | 1 | 2022-11-24 | 2022-11-24 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Physical Inspection Step API | 3585 | 2022-11-27 | 2022-11-30 | 0 | 2022-11-27 | 2022-11-30 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Product, By-Product Lot creation and material transaction | 3586 | 2022-11-28 | 2022-11-30 | 0 | 2022-11-29 | 2022-11-30 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Activity (IF/LRF/CCM) planned and actual data insert API | 3587 | 2022-11-30 | 2022-11-30 | 1 | 2022-11-30 | 2022-11-30 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Resource (IF/LRF/CCM) planned and actual data insert/update API | 3588 | 2022-12-01 | 2022-11-30 | 1 | 2022-12-04 | 2022-12-04 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Sample creation API | 3589 | 2022-12-05 | 2022-12-05 | 1 | 2022-12-05 | 2022-12-05 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | ALL Chemistry data (IF/LRF/CCM) insert API | 3590 | 2022-12-06 | 2022-12-05 | 1 | 2022-12-07 | 2022-12-07 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Physical Inspection quality data entry API | 3591 | 2022-12-08 | 2022-12-07 | 1 | 2022-12-08 | 2022-12-12 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Quality Disposition API | 3592 | 2022-12-11 | 2022-12-12 | 0 | 2022-12-11 | 2022-12-12 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Activity/Step completion API | 3593 | 2022-12-12 | 2022-12-12 | 1 | 2022-12-12 | 2022-12-12 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Batch completion and close API | 3594 | 2022-12-13 | 2022-12-12 | 1 | 2022-12-13 | 2022-12-14 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Package development | 3595 | 2022-12-14 | 2022-12-14 | 1 | 2022-12-15 | 2022-12-15 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Validation Check | 3596 | 2022-12-17 | 2022-12-19 | 0 | 2022-12-19 | 2022-12-19 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Process/Reprocess | 3597 | 2022-12-20 | 2022-12-19 | 1 | 2022-12-22 | 2022-12-22 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | Source data analysis | Source data analysis | 3574 | 2022-10-23 | 2022-10-26 | 0 | 2022-10-23 | 2022-10-26 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | Architectural design | Architectural design | 3575 | 2022-10-24 | 2022-10-26 | 0 | 2022-10-25 | 2022-10-26 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | L2E-Middleware Database design and Execution | L2E-Middleware Database design and Execution | 3576 | 2022-10-26 | 2022-10-26 | 1 | 2022-10-27 | 2022-11-03 | 0 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | CPI | Create iFlow in CPI | 3614 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | API | Create API to receive payroll data | 3615 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-22 | 2022-09-22 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Mapping Pay item and Percentage logic | 3616 | 2022-09-24 | 2022-09-24 | 1 | 2022-09-26 | 2022-09-26 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Create new evaluation with updated event reason | 3617 | 2022-09-26 | 2022-09-26 | 1 | 2022-09-29 | 2022-09-29 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Payroll process and Check | 3618 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-01 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | PF and Oracle Invoice process | 3619 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-01 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Create Company & DB | 3621 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-03 | 2022-10-03 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Journal and voucher setup | 3622 | 2022-10-03 | 2022-10-03 | 1 | 2022-10-04 | 2022-10-04 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Ledger setup | 3623 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-05 | 2022-10-05 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in SF integration procedure | 3624 | 2022-10-05 | 2022-10-05 | 1 | 2022-10-06 | 2022-10-06 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in iBMS HRIS Employee Form | 3625 | 2022-10-08 | 2022-10-08 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in iBMS HRIS Voucher Forms | 3626 | 2022-10-09 | 2022-10-09 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Data Preparation | Opening data upload | 3627 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-12 | 2022-10-12 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Data Preparation | Create payitems and company mapping | 3628 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Report | Employeewise WPPF Report | 3629 | 2022-10-12 | 2022-10-12 | 1 | 2022-10-13 | 2022-10-13 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Report | Change Accounting report for WPPF | 3630 | 2022-10-13 | 2022-10-13 | 1 | 2022-10-16 | 2022-10-16 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Create Setup | Create Table | 3650 | 2022-09-02 | 2022-09-02 | 1 | 2022-09-02 | 2022-09-02 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Create Setup | Create SQL Jobs | 3651 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Architecture | Create .NET Core project for CM | 3652 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Develop | Develop classed to process CSV files | 3653 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Implemenation | Integrate in Tax Certificate Project | 3654 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Implemenation | Integrate in Kolkata Attendance Process | 3655 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Concurrent Manager Desktop | Concurrent Manager Project | Create Concurrent for CSV File Upload | 3657 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Policy Implementation | Create shift as per policy | 3658 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-13 | 2022-10-13 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Policy Implementation | Attendace data configuration as per policy | 3659 | 2022-10-16 | 2022-10-16 | 1 | 2022-10-18 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | Configuration in Attendance DB | 3660 | 2022-10-18 | 2022-10-18 | 1 | 2022-10-18 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | TimeZone change in Lead Management API | 3661 | 2022-10-19 | 2022-10-19 | 1 | 2022-10-19 | 2022-10-19 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | File Upload option in HRIS | 3662 | 2022-10-20 | 2022-10-20 | 1 | 2022-10-20 | 2022-10-20 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | Process data in HRIS | 3663 | 2022-10-21 | 2022-10-21 | 1 | 2022-10-22 | 2022-10-22 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | WPPF Individual Tax Confirmation | Process and Query Preparation | 3505 | 2022-10-13 | 2022-10-06 | 1 | 2022-10-13 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Change in SF integration procedure Change in iBMS HRIS EmployeeForm Change in iBMS HRIS Voucher Forms | 3996 | 2023-03-11 | 2023-03-11 | 1 | 2023-03-14 | 2023-03-14 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Journal Voucher &Ledger Setup | 3995 | 2023-03-04 | 2023-03-04 | 1 | 2023-03-10 | 2023-03-10 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Claim Form | 3997 | 2023-03-15 | 2023-03-15 | 1 | 2023-03-23 | 2023-03-23 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Claim to Voucher by Data Load | 3998 | 2023-03-25 | 2023-03-25 | 1 | 2023-03-27 | 2023-03-27 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Opening data upload | 3999 | 2023-03-27 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-30 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Report | Summary & Details Report | 4000 | 2023-04-02 | 2023-04-02 | 1 | 2023-04-04 | 2023-04-04 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Create Company & DB | 3994 | 2023-03-01 | 2023-03-01 | 1 | 2023-03-04 | 2023-03-04 | 1 | 17020000005213 | Syed Saiful Haque
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | Requirement Analysis | Review Initial User Report Template | 4002 | 2023-04-08 | 2023-04-06 | 1 | 2023-04-08 | 2023-04-06 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | Feasibility Study | Feasibility study | 4003 | 2023-04-08 | 2023-04-06 | 1 | 2023-04-08 | 2023-04-06 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | KPI Identification | Review KPI | 3857 | 2023-02-05 | 2023-02-05 | 1 | 2023-02-06 | 2023-02-05 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization(Phase-2) | Requirement Analysis | Review Change Request for Existing KPI | 3992 | 2023-04-04 | 2023-04-04 | 1 | 2023-04-05 | 2023-04-04 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | Report Template Design | Verify Report Template Design | 4007 | 2023-04-10 | 2023-04-09 | 1 | 2023-04-10 | 2023-04-09 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Requirment Analysis | Review Initial User Report Template | 3854 | 2023-01-28 | 2023-01-28 | 1 | 2023-01-29 | 2023-01-28 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Feasibility Study | Feasibility study | 3855 | 2023-01-30 | 2023-01-30 | 1 | 2023-01-31 | 2023-01-30 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Report Template Design | Verify Report Template Design | 3859 | 2023-02-11 | 2023-02-11 | 1 | 2023-02-12 | 2023-02-14 | 0 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Warehouse Design | Verify technical design plan | 3867 | 2023-03-02 | 2023-03-09 | 0 | 2023-03-02 | 2023-03-09 | 0 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Development | ETL Development | 3868 | 2023-03-05 | 2023-03-09 | 0 | 2023-03-09 | 2023-03-09 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Warehouse Design | Verify technical design plan | 4014 | 2023-04-13 | 2023-04-09 | 1 | 2023-04-13 | 2023-04-09 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Development | ETL Development | 4015 | 2023-04-12 | 2023-04-09 | 1 | 2023-04-16 | 2023-04-11 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Testing | ETL Test | 4016 | 2023-04-16 | 2023-04-11 | 1 | 2023-04-16 | 2023-04-11 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Requirment Analysis | Review Change Request for Existing KPI | 4025 | 2023-04-26 | 2023-04-27 | 0 | 2023-04-28 | 2023-04-27 | 1 | 17020000009961 | A.B.M. Nahidul Islam
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | KPI Identification | Review KPI | 4005 | 2023-04-09 | 2023-04-08 | 1 | 2023-04-09 | 2023-04-08 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization For Region wise, ZSH wise Sales performance | Requirment Analysis | Review Change Request for Existing KPI | 4036 | 2023-04-26 | 2023-04-27 | 0 | 2023-04-28 | 2023-04-27 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization For Region wise, ZSH wise Sales performance | Feasibility Study | Feasibility study | 4037 | 2023-04-26 | 2023-04-27 | 0 | 2023-04-28 | 2023-04-27 | 1 | 17020000009961 | A.B.M. Nahidul Islam
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization For Region wise, ZSH wise Sales performance | KPI Identification | Review KPI | 4039 | 2023-04-30 | 2023-04-30 | 1 | 2023-05-02 | 2023-04-30 | 1 | 17020000009961 | A.B.M. Nahidul Islam
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | ETL for Steels-2 | Server configuration and environment creation | 3577 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000009961 | A.B.M. Nahidul Islam
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | ETL for Steels-2 | Query development for data import | 3578 | 2022-10-30 | 2022-10-30 | 1 | 2022-11-02 | 2022-11-02 | 1 | 17020000009961 | A.B.M. Nahidul Islam
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | ETL for Steels-2 | Populate data to intermediate and interface | 3579 | 2022-11-03 | 2022-11-03 | 1 | 2022-11-07 | 2022-11-06 | 1 | 17020000009961 | A.B.M. Nahidul Islam
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | ETL for Steels-2 | Load plan design. Development & Schedule | 3580 | 2022-11-08 | 2022-11-07 | 1 | 2022-11-16 | 2022-11-13 | 1 | 17020000009961 | A.B.M. Nahidul Islam
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | ETL for Steels-2 | Load Plan Test | 3581 | 2022-11-17 | 2022-11-13 | 1 | 2022-11-17 | 2022-11-17 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Requirment Analysis | Review Initial User Report Template | 3512 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-10 | 2022-08-10 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Feasibility Study | Feasibility study | 3513 | 2022-08-11 | 2022-08-10 | 1 | 2022-08-12 | 2022-08-11 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | KPI Identification | Identify the KPI | 3514 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-15 | 2022-08-14 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | KPI Identification | Review KPI | 3515 | 2022-08-20 | 2022-08-20 | 1 | 2022-08-21 | 2022-08-20 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Report Template Design | Review Report Template Design | 3516 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-23 | 2022-08-22 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Report Template Design | Verify Report Template Design | 3517 | 2022-08-24 | 2022-08-24 | 1 | 2022-08-25 | 2022-08-24 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Report Template Design | Approve Report Template Design | 3518 | 2022-08-26 | 2022-08-25 | 1 | 2022-08-27 | 2022-08-25 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | KPI Review | Finalize KPI, Dimension | 3519 | 2022-08-28 | 2022-08-28 | 1 | 2022-09-01 | 2022-08-31 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Initial Assesment and Requirement Finalization | Development Phase Define | Phase Identification | 3520 | 2022-09-02 | 2022-09-01 | 1 | 2022-09-03 | 2022-09-01 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Source Validation | Source Mapping | 3521 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-05 | 2022-09-04 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Source Validation | Sample KPI data population based on source mapping | 3522 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-12 | 2022-10-12 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Source Validation | Sample data validation | 3523 | 2022-10-13 | 2022-10-13 | 1 | 2022-10-19 | 2022-10-19 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Warehouse Design | Prepare technical design plan | 3524 | 2022-10-20 | 2022-10-20 | 1 | 2022-10-25 | 2022-10-25 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Development | ETL Development | 3526 | 2022-09-17 | 2022-09-17 | 1 | 2022-09-20 | 2022-09-20 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Signed-Off | Signed-Off/Formal Confirmation | 3529 | 2022-09-28 | 2022-09-28 | 1 | 2022-09-29 | 2022-09-29 | 1 | 17020000009961 | A.B.M. Nahidul Islam
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Signed-Off | Loadplan Execution Follow-up | 3530 | 2022-09-30 | 2022-10-31 | 0 | 2022-10-01 | 2022-10-01 | 1 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | Requirment Analysis | Review Initial User Report Template | 4273 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-15 | 2023-06-15 | 1 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | Feasibility Study | Feasibility study | 4274 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-15 | 2023-06-15 | 1 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | KPI Identification | Review KPI | 4276 | 2023-06-15 | 2023-06-17 | 0 | 2023-06-15 | 2023-06-17 | 0 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | Report Template Design | Verify Report Template Design | 4278 | 2023-06-17 | 2023-06-17 | 1 | 2023-06-17 | 2023-06-17 | 1 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Warehouse Design | Verify technical design plan | 4286 | 2023-06-21 | 2023-06-22 | 0 | 2023-06-21 | 2023-06-22 | 0 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Development | ETL Development | 4287 | 2023-06-21 | 2023-06-22 | 0 | 2023-06-22 | 2023-06-22 | 1 | 17020000009961 | A.B.M. Nahidul Islam
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Development | Report Development | 4288 | 2023-06-22 | 2023-06-22 | 1 | 2023-06-25 | 2023-06-25 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Testing | Report Test | 4289 | 2023-06-25 | 2023-06-25 | 1 | 2023-06-25 | 2023-06-25 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Signed-Off | Loadplan Execution Follow-up | 4291 | 2023-06-26 | 2023-06-26 | 1 | 2023-06-27 | 2023-06-26 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | KPI Review | Finalize KPI, Dimension | 4280 | 2023-06-17 | 2023-06-17 | 1 | 2023-06-18 | 2023-06-18 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | Development Phase Define | Phase Identification | 4281 | 2023-06-18 | 2023-06-18 | 1 | 2023-06-18 | 2023-06-18 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Source Validation | Source Mapping | 4282 | 2023-06-19 | 2023-06-19 | 1 | 2023-06-19 | 2023-06-19 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Source Validation | Sample KPI data population based on source mapping | 4283 | 2023-06-19 | 2023-06-19 | 1 | 2023-06-19 | 2023-06-19 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Dealer Categorization | Warehouse Design | Prepare technical design plan | 4285 | 2023-06-20 | 2023-06-22 | 0 | 2023-06-21 | 2023-06-22 | 0 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | Report Template Design | Review Report Template Design | 4277 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-15 | 2023-06-15 | 1 | 17020000014076 | Pritom Barua
Please prepare a report for Dealer Categorization, here attached the categorization parameters. | Dealer Categorization | Initial Assesment and Requirement Finalization | KPI Identification | Identify the KPI | 4275 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-15 | 2023-06-15 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Source Validation | Source Mapping | 3531 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-02 | 2022-09-02 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Source Validation | Sample KPI data population based on source mapping | 3532 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Source Validation | Sample data validation | 3533 | 2022-09-05 | 2022-09-05 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Warehouse Design | Prepare technical design plan | 3534 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-09 | 2022-09-09 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Development | ETL Development | 3536 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-15 | 2022-09-13 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Development | Report Development | 3537 | 2022-09-16 | 2022-09-16 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Signed-Off | Signed-Off/Formal Confirmation | 3539 | 2022-09-22 | 2022-09-22 | 1 | 2022-09-23 | 2022-09-22 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Booking Analysis (Phase-2) | Signed-Off | Loadplan Execution Follow-up | 3540 | 2022-09-24 | 2022-09-24 | 1 | 2022-09-25 | 2022-09-25 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Source Validation | Source Mapping | 3541 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-02 | 2022-09-02 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Source Validation | Sample KPI data population based on source mapping | 3542 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Source Validation | Sample data validation | 3543 | 2022-09-05 | 2022-09-05 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Warehouse Design | Prepare technical design plan | 3544 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-09 | 2022-09-09 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Development | ETL Development | 3546 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-15 | 2022-09-13 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Development | Report Development | 3547 | 2022-09-16 | 2022-09-16 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Signed-Off | Signed-Off/Formal Confirmation | 3549 | 2022-09-22 | 2022-09-22 | 1 | 2022-09-23 | 2022-09-22 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Pending Analysis (Phase-3) | Signed-Off | Loadplan Execution Follow-up | 3550 | 2022-09-24 | 2022-09-24 | 1 | 2022-09-25 | 2022-09-25 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Source Validation | Source Mapping | 3551 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-02 | 2022-09-02 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Source Validation | Sample KPI data population based on source mapping | 3552 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Source Validation | Sample data validation | 3553 | 2022-09-05 | 2022-09-05 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Warehouse Design | Prepare technical design plan | 3554 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-09 | 2022-09-08 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Development | ETL Development | 3556 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-15 | 2022-09-13 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Development | Report Development | 3557 | 2022-09-16 | 2022-09-17 | 0 | 2022-09-18 | 2022-09-18 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Signed-Off | Signed-Off/Formal Confirmation | 3559 | 2022-09-22 | 2022-09-22 | 1 | 2022-09-23 | 2022-09-23 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Stock Analysis (Phase-4) | Signed-Off | Loadplan Execution Follow-up | 3560 | 2022-09-24 | 2022-09-24 | 1 | 2022-09-25 | 2022-09-25 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Source Validation | Source Mapping | 3561 | 2022-09-26 | 2022-09-26 | 1 | 2022-09-27 | 2022-09-27 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Source Validation | Sample KPI data population based on source mapping | 3562 | 2022-09-28 | 2022-09-28 | 1 | 2022-09-29 | 2022-09-29 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Source Validation | Sample data validation | 3563 | 2022-09-30 | 2022-09-28 | 1 | 2022-10-02 | 2022-09-29 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Warehouse Design | Prepare technical design plan | 3564 | 2022-10-03 | 2022-10-03 | 1 | 2022-10-04 | 2022-10-04 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Development | ETL Development | 3566 | 2022-10-07 | 2022-10-08 | 0 | 2022-10-10 | 2022-10-10 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Development | Report Development | 3567 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-13 | 2022-10-13 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Signed-Off | Signed-Off/Formal Confirmation | 3569 | 2022-10-17 | 2022-10-17 | 1 | 2022-10-18 | 2022-10-18 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Credit Limit Analysis (Phase-5) | Signed-Off | Loadplan Execution Follow-up | 3570 | 2022-10-19 | 2022-10-19 | 1 | 2022-10-20 | 2022-10-20 | 1 | 17020000014076 | Pritom Barua
To provide the KPI Matrix details. | Application for Daily Sales, Booking, Pending, Stock and Credit Limit Analysis | Daily Sales Analysis (Phase-1) | Development | Report Development | 3527 | 2022-10-31 | 2022-11-01 | 0 | 2022-11-10 | 2022-11-10 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization For Region wise, ZSH wise Sales performance | KPI Review | Finalize KPI, Dimension | 4040 | 2023-05-02 | 2023-05-02 | 1 | 2023-05-03 | 2023-05-02 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization For Region wise, ZSH wise Sales performance | KPI Identification | Identify the KPI Sources for CR | 4038 | 2023-04-27 | 2023-04-27 | 1 | 2023-04-30 | 2023-04-27 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | Report Template Design | Review Report Template Design | 4006 | 2023-04-09 | 2023-04-08 | 1 | 2023-04-09 | 2023-04-08 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | KPI Identification | Identify the KPI Sources for CR | 4026 | 2023-04-27 | 2023-04-27 | 1 | 2023-04-30 | 2023-04-27 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Region wise, ZSH wise Sales performance | Source Validation | Source Mapping for CR | 4027 | 2023-05-02 | 2023-04-30 | 1 | 2023-05-03 | 2023-04-30 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Region wise, ZSH wise Sales performance | Source Validation | Sample KPI data population based on CR source mapping | 4028 | 2023-05-02 | 2023-04-30 | 1 | 2023-05-03 | 2023-05-02 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Region wise, ZSH wise Sales performance | Warehouse Design | Prepare technical design plan | 4030 | 2023-05-06 | 2023-05-06 | 1 | 2023-05-07 | 2023-05-06 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Development | Report Development | 4017 | 2023-04-13 | 2023-04-09 | 1 | 2023-04-17 | 2023-04-11 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Testing | Report Test | 4018 | 2023-04-18 | 2023-04-11 | 1 | 2023-04-18 | 2023-04-12 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Signed-Off | Load plan Execution Follow-up | 4020 | 2023-04-20 | 2023-04-12 | 1 | 2023-04-20 | 2023-04-12 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Development | Report Development | 3869 | 2023-03-11 | 2023-02-22 | 1 | 2023-03-14 | 2023-02-28 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Testing | Report Test | 3870 | 2023-03-15 | 2023-03-09 | 1 | 2023-03-16 | 2023-03-15 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Signed-Off | Loadplan Execution Follow-up | 3872 | 2023-03-20 | 2023-03-15 | 1 | 2023-03-23 | 2023-03-19 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | KPI Review | Finalize KPI, Dimension | 3861 | 2023-02-14 | 2023-02-12 | 1 | 2023-02-16 | 2023-02-12 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Development Phase Define | Phase Identification | 3862 | 2023-02-19 | 2023-02-12 | 1 | 2023-02-19 | 2023-02-12 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Source Validation | Source Mapping | 3863 | 2023-02-20 | 2023-02-12 | 1 | 2023-02-22 | 2023-02-12 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Source Validation | Sample KPI data population based on source mapping | 3864 | 2023-02-23 | 2023-02-14 | 1 | 2023-02-25 | 2023-02-14 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Daily Sales Analysis for COO | Warehouse Design | Prepare technical design plan | 3866 | 2023-02-28 | 2023-02-14 | 1 | 2023-03-01 | 2023-02-14 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | KPI Identification | Identify the KPI | 3856 | 2023-02-01 | 2023-02-01 | 1 | 2023-02-02 | 2023-02-02 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | KPI Review | Finalize KPI, Dimension | 4009 | 2023-04-10 | 2023-04-08 | 1 | 2023-04-10 | 2023-04-08 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Source Validation | Source Mapping | 4010 | 2023-04-10 | 2023-04-08 | 1 | 2023-04-10 | 2023-04-08 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Source Validation | Sample KPI data population based on source mapping | 4011 | 2023-04-11 | 2023-04-09 | 1 | 2023-04-11 | 2023-04-09 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Wires Sales Report | Warehouse Design | Prepare technical design plan | 4013 | 2023-04-13 | 2023-04-09 | 1 | 2023-04-13 | 2023-04-09 | 1 | 17020000014076 | Pritom Barua
We need to Develop a Sales Analysis Report for COO sir. User Provide a sample report template "Copy of Daily Sales report.xlsx" (attached with ticket) with specifying required KPI . We need to create a project plan according to BI Development SOP. Thank you | Key insights: Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assesment and Requirement Finalization | Report Template Design | Review Report Template Design | 3858 | 2023-02-07 | 2023-02-07 | 1 | 2023-02-09 | 2023-02-08 | 1 | 17020000014076 | Pritom Barua
One template for BI Report development for Wires Business | Key insights : Sales performance, Sales by product, Sales by segment, Sales team performance | Initial Assessment and Requirement Finalization | KPI Identification | Identify the KPI | 4004 | 2023-04-08 | 2023-04-06 | 1 | 2023-04-09 | 2023-04-06 | 1 | 17020000014076 | Pritom Barua
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Monthly Tax Summary | Report Design and Development | 3494 | 2022-09-15 | 2022-09-14 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000014497 | Md. Pervez Meah
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Production Migrate | 1. Form 2. Function 3. Report | 1. Form 2. Function 3. Report | 3843 | 2023-01-10 | 2023-01-10 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | WPPF Individual Tax Confirmation | Report Design and Development | 3506 | 2022-10-16 | 2022-09-27 | 1 | 2022-10-17 | 2022-09-27 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | WPPF Individual Tax Confirmation | Report API and UI | 3507 | 2022-10-17 | 2022-09-27 | 1 | 2022-10-17 | 2022-09-27 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | Process Job Monitor | API | 3508 | 2022-10-18 | 2022-09-25 | 1 | 2022-10-18 | 2022-09-25 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | Process Job Monitor | UI | 3509 | 2022-10-19 | 2022-09-25 | 1 | 2022-10-19 | 2022-09-25 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | AIT Eligibility Setup | AIT Rule and % setup | Create new Table in Oracle db for AIT Rules and AIT rate function | 3969 | 2023-04-03 | 2023-04-03 | 1 | 2023-04-03 | 2023-04-03 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | AIT Eligibility Setup | AIT Rule and % setup | Create New two field for AIT Rules in SOF form in sales ebs | 4041 | 2023-04-04 | 2023-04-04 | 1 | 2023-04-05 | 2023-04-05 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | AIT Eligibility Setup | AIT Rule and % setup | Create New two field for AIT Rules in SOF form in sales ebs ( Form customer order) | 4042 | 2023-04-05 | 2023-04-05 | 1 | 2023-04-06 | 2023-04-06 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Environment setup for AIT | Create SO and finish the order with delivery and create invoice | 4043 | 2023-04-08 | 2023-04-08 | 1 | 2023-04-13 | 2023-04-13 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Calculate AIT | Calculate AIT on Reload Procedure(Invoice) AIT Reserve amount will be calculated for Full invoice amount initially | 4044 | 2023-04-16 | 2023-04-16 | 1 | 2023-05-02 | 2023-05-02 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Update Create MR Form | Update AIT Amount source in create mr application form | 4046 | 2023-05-02 | 2023-05-02 | 1 | 2023-05-02 | 2023-05-02 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Update Create MR Form | Resize MR File Upload Process | 4047 | 2023-05-03 | 2023-05-03 | 1 | 2023-05-06 | 2023-05-06 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Show Calculated AIT | Display calculated AIT on unappliead MR and CM Form on OMR application | 4048 | 2023-05-07 | 2023-05-07 | 1 | 2023-05-08 | 2023-05-08 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Show Calculated AIT | AIT Reserve Amount Source need to be changed in procedure () | 4049 | 2023-05-09 | 2023-05-09 | 1 | 2023-05-10 | 2023-05-10 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Recalculate AIT | AIT Change History | When AIT rules chanage data add in new history table | 4051 | 2023-05-16 | 2023-05-16 | 1 | 2023-05-18 | 2023-05-18 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Recalculate AIT | New Procedure | Create a Procedure to recalculate after change percentage of AIT | 4052 | 2023-05-20 | 2023-05-20 | 1 | 2023-05-22 | 2023-05-22 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Report | Existing report change | Change in InvoiceAgingReport and OMRMoneyRegister report | 4053 | 2023-05-23 | 2023-05-23 | 1 | 2023-05-24 | 2023-05-24 | 1 | 17020000014497 | Md. Pervez Meah
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Report | New Report | Create AIT Report as FDD | 4054 | 2023-05-25 | 2023-05-25 | 1 | 2023-05-31 | 2023-05-31 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Data.aspx | Add parameterised query in all raw query | 3665 | 2022-11-20 | 2022-11-20 | 1 | 2022-11-30 | 2022-11-30 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | SOF Entry | Add parameterised query in all raw query | 3666 | 2022-12-01 | 2022-12-01 | 1 | 2022-12-12 | 2022-12-12 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Customer Complaint | Add parameterised query in all raw query | 3667 | 2022-12-12 | 2022-12-12 | 1 | 2022-12-13 | 2022-12-13 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Password Change | Add parameterised query in all raw query | 3668 | 2022-12-14 | 2022-12-14 | 1 | 2022-12-15 | 2022-12-15 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Payment Register | Add parameterised query in all raw query | 3669 | 2022-12-17 | 2022-12-17 | 1 | 2022-12-17 | 2022-12-17 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Do Unlock | Add parameterised query in all raw query | 3670 | 2022-12-18 | 2022-12-18 | 1 | 2022-12-18 | 2022-12-18 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Credit Hold | Add parameterised query in all raw query | 3671 | 2022-12-19 | 2022-12-19 | 1 | 2022-12-19 | 2022-12-19 | 1 | 17020000014497 | Md. Pervez Meah
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Report | Add parameterised query in all raw query | 3672 | 2022-12-20 | 2022-12-20 | 1 | 2023-01-10 | 2023-01-10 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | MMT VTS API | Create Setup | Create API and Setup Database | 3642 | 2022-10-20 | 2022-10-20 | 1 | 2022-10-20 | 2022-10-20 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | MMT VTS API | Authentication | Create Login Endpoint with token | 3643 | 2022-10-22 | 2022-10-22 | 1 | 2022-10-22 | 2022-10-22 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | MMT VTS API | Create USER API | Create Endpoint to get challan info | 3644 | 2022-10-23 | 2022-10-23 | 1 | 2022-10-23 | 2022-10-23 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | MMT VTS API | Create USER API | Create Endpoint to insert challan info | 3645 | 2022-10-24 | 2022-10-24 | 1 | 2022-10-24 | 2022-10-24 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | MMT VTS API | Create USER API | Create Endpoint to insert sms data | 3646 | 2022-10-25 | 2022-10-25 | 1 | 2022-10-25 | 2022-10-25 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | UAT | UAT | UAT | 3647 | 2022-10-26 | 2022-10-26 | 1 | 2022-10-26 | 2022-10-26 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | SMS | SMS | SMS to be sent to respective stakeholders | 3648 | 2022-11-03 | 2022-11-03 | 1 | 2022-11-13 | 2022-11-13 | 1 | 17020000014497 | Md. Pervez Meah
Please develop a system to provide SO information, loading, unloading, breakdown SMS and tracking link to get info regarding the transport. | In-house application (Sales portal/apps, customer portal/app, SMS Service) integration with Vehicle tracking and follow-up application (by MM Transport) to capture challan wise vehicle tracking, follow-up SMS like delay delivery, breakdown, reach on destination, unloading completed, etc, and a central dashboard. | Web | Web | Tracking the vehicle by using the link shared by transporter | 3649 | 2022-11-03 | 2022-11-03 | 1 | 2022-11-13 | 2022-11-13 | 1 | 17020000014497 | Md. Pervez Meah
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Check constraint Delivery Challan print with QR Code | Check constraint Delivery Challan print with QR Code | 3811 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-12 | 2022-10-12 | 1 | 17020000014497 | Md. Pervez Meah
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Save QR Code from the Delivery Challan Form | Save QR Code from the Delivery Challan Form | 3812 | 2023-01-10 | 2023-01-10 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014497 | Md. Pervez Meah
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Print QR Code on the Delivery Challan Report | Print QR Code on the Delivery Challan Report | 3813 | 2023-01-10 | 2023-01-10 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Tax Deduction Summary | Report Design and Development | 3503 | 2022-10-11 | 2022-09-24 | 1 | 2022-10-12 | 2022-09-25 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Tax Deduction Summary | Report API and UI | 3504 | 2022-10-12 | 2022-09-24 | 1 | 2022-10-12 | 2022-09-25 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report Perquisite | Report Design and Development | 3500 | 2022-10-06 | 2022-09-26 | 1 | 2022-10-09 | 2022-09-26 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report Perquisite | Report API and UI | 3501 | 2022-10-10 | 2022-09-26 | 1 | 2022-10-10 | 2022-09-26 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report 108 | Report Design and Development | 3497 | 2022-10-03 | 2022-09-26 | 1 | 2022-10-04 | 2022-09-26 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report 108 | Report API and U | 3498 | 2022-10-05 | 2022-09-26 | 1 | 2022-10-05 | 2022-09-26 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Monthly Tax Summary | Report API and UI | 3495 | 2022-09-15 | 2022-09-15 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Master Setup UI | Allowance Setup Form | Create Form setup api and front end | 3198 | 2022-09-12 | 2022-09-11 | 1 | 2022-09-14 | 2022-09-12 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Master Setup UI | AIT entry form | Create Form setup api and front end | 3199 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Master Setup UI | Refund Entry form/Tax Rebate Entry | Create Form setup api and front end | 3200 | 2022-09-10 | 2022-09-10 | 1 | 2022-09-11 | 2022-09-11 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Master Setup UI | Car Enititalment entry form | Create Form setup api and front end | 3201 | 2022-09-06 | 2022-09-06 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Master Setup UI | Upload WPPF Data form | Create Form setup api and front end | 3202 | 2022-09-21 | 2022-09-21 | 1 | 2022-09-22 | 2022-09-22 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Upload UI | Upload Signed Challan | Upload Signed Challan | 3207 | 2022-09-18 | 2022-09-18 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Upload UI WPPF | Upload UI | Upload UI | 3209 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-20 | 2022-09-20 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Caculation of Tax | Necessary ranges and boundaries (Master setup) (backend) | Necessary ranges and boundaries (Master setup) (backend) | 3210 | 2022-09-25 | 2022-09-25 | 1 | 2022-09-26 | 2022-09-26 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Caculation of Tax | Car Holder AIT calculation | Car Holder AIT calculation | 3211 | 2022-09-27 | 2022-09-11 | 1 | 2022-09-28 | 2022-09-12 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Caculation of Tax | create respective table for calculation | create respective table for calculation | 3212 | 2022-09-29 | 2022-09-01 | 1 | 2022-10-02 | 2022-09-04 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Caculation of Tax | prepare function and procedure of each pay item | prepare function and procedure of each pay item | 3213 | 2022-10-03 | 2022-08-11 | 1 | 2022-10-04 | 2022-08-14 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | download by user | download by user | 3216 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | re-calculation of tax after aparaisal | re-calculation of tax after aparaisal | 3219 | 2022-10-16 | 2022-08-15 | 1 | 2022-10-16 | 2022-08-18 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | submit tax to payroll | submit tax to payroll | 3220 | 2022-10-17 | 2022-07-07 | 1 | 2022-10-18 | 2022-07-14 | 1 | 17020000014497 | Md. Pervez Meah
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | Publish tax certificate | Publish tax certificate | 3221 | 2022-10-19 | 2022-10-17 | 1 | 2022-10-19 | 2022-10-17 | 1 | 17020000014497 | Md. Pervez Meah
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | For Year end appraisal we need a report contains various rating. Sharing the format for your easy understanding. [Ticket NO: 133023] | 3329 | 2022-07-07 | 2022-07-07 | 1 | 2022-07-13 | 2022-07-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Group Setup, Param Setup | 2596 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Permissions Setup | Permission on ORG, Region, Common Budget, | 2601 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-14 | 2022-08-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Nature Of Accounts Setup | Common budget NoA setup, | 2603 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-17 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item type setup | 2597 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Ratio Setup | 2598 | 2022-09-13 | 2022-09-13 | 1 | 2022-09-15 | 2022-09-15 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Company Setup | 2599 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | PBCPM(Planing Budget….) Common Budget Setup | Common budget NoA setup, | 2605 | 2022-08-21 | 2022-08-21 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Sales Budget Setup with Region. | Region wise setup. | 2606 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Multi layer approval | 2612 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-25 | 2022-08-25 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Submit Budget | Submit budget with validation and save | 2611 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Setup | User and workflow and cost center and location setup, ADD Edit And delete | 2600 | 2022-08-10 | 2022-08-10 | 1 | 2022-08-12 | 2022-08-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Draft Mode Save | Draft mode save from file and UI. | 2609 | 2022-07-03 | 2022-07-03 | 1 | 2022-07-04 | 2022-07-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2610 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-21 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | PBCPM Comments entry | 2613 | 2022-08-23 | 2022-08-02 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Notification Mail | 2614 | 2022-08-25 | 2022-08-25 | 1 | 2022-08-27 | 2022-08-27 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Work flow Stage visibility | 2615 | 2022-08-28 | 2022-08-28 | 1 | 2022-08-28 | 2022-08-28 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Draft Mode Save | Draft mode save from file and UI. | 2616 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2617 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-30 | 2022-08-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Submit Budget | Submit budget with validation and save | 2618 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Multi layer approval | 2619 | 2022-08-31 | 2022-08-31 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | PBCPM Comments entry | 2620 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-01 | 2022-09-01 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Notification Mail | 2621 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Work flow Stage visibility | 2622 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-05 | 2022-09-05 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | File template management | File template Upload as per NoA assignment | 2624 | 2022-09-06 | 2022-09-06 | 1 | 2022-09-06 | 2022-09-06 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Draft Mode Save | Draft mode save from file and UI. | 2625 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2626 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Submit Budget | Submit budget with validation and save | 2627 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Multi layer approval | 2628 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-11 | 2022-09-11 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | PBCPM Comments entry | 2629 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Notification Mail | 2630 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Work flow Stage visibility | 2631 | 2022-09-12 | 2022-09-11 | 1 | 2022-09-13 | 2022-09-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template download as per NoA assignment | 2632 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template Upload as per NoA assignment | 2633 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Draft Mode Save | Draft mode save from file and UI. | 2634 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2635 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Submit Budget | Submit budget with validation and save | 2636 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Multi layer approval | 2637 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | PBCPM Comments entry | 2638 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Notification Mail | 2639 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Work flow Stage visibility | 2640 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template download as per NoA assignment | 2650 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template Upload as per NoA assignment | 2651 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Draft Mode Save | Draft mode save from file and UI. | 2652 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2653 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Submit Budget | Submit budget with validation and save | 2654 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Multi layer approval | 2655 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | PBCPM Comments entry | 2656 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Notification Mail | 2657 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Work flow Stage visibility | 2658 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Review for previous process | Transfar previous reviews data to half yearly review. | 2673 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-08 | 2022-09-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Open Budget period | Budget setup activty by PBCPM | 2674 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Actual consumption for current year. | Pop View for actual consumption | 2675 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Access wise query preparation. | 2681 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-14 | 2022-09-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget view API | 2682 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget View UI | 2683 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | As discussed, please upload bulk employees for proxy management. Ticket Details [Ticket NO: 139489] | 3571 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Add Proxy for HR person | 3572 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | UI Design and Development | 3598 | 2022-12-26 | 2022-12-26 | 1 | 2023-01-02 | 2023-01-02 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Physical Inspection | 3599 | 2023-01-03 | 2023-01-03 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch details | 3600 | 2023-01-16 | 2023-01-16 | 1 | 2023-01-22 | 2023-01-22 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch correction | 3601 | 2023-01-23 | 2023-01-23 | 1 | 2023-01-30 | 2023-01-30 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Formula item configuration and modification | 3602 | 2023-01-31 | 2023-01-31 | 1 | 2023-02-02 | 2023-02-02 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template download as per NoA assignment | 2659 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template Upload as per NoA assignment | 2660 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Draft Mode Save | Draft mode save from file and UI. | 2661 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2662 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Submit Budget | Submit budget with validation and save | 2663 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Multi layer approval | 2664 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | PBCPM Comments entry | 2665 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Notification Mail | 2666 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Work flow Stage visibility | 2669 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template Upload as per submitted capital budget. | 2668 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template download as per submitted capital budget | 2667 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | UAT | UAT | UAT | 2690 | 2022-11-08 | NULL | 0 | 2022-11-10 | NULL | 0 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We have found error message when testing new goal plan 22-23 in the production system. Need to raise ticket to SAP. Please support us in this issue.. Ticket Details [Ticket NO: 136980] | 3510 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We need to update some features in the existing performance form (incorporate comments in +1 Manager, sign-off step) which was observed last year & discussed with you. Please support us in doing this in the system to start the new goal plan 22-23. Thank you Ticket Details [Ticket NO: 137115] | 3511 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-30 | 2022-09-30 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | Prepare ERD | 4131 | 2023-05-10 | 2023-05-10 | 1 | 2023-05-11 | 2023-05-11 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | New DB Object | 4132 | 2023-05-14 | 2023-05-14 | 1 | 2023-05-15 | 2023-05-15 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | API | Create API Structure with CQRS Pattern | 4133 | 2023-05-16 | 2023-05-16 | 1 | 2023-05-17 | 2023-05-17 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | UI | Angular Project setup + Login | 4134 | 2023-05-18 | 2023-05-18 | 1 | 2023-05-20 | 2023-05-20 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Authorization Setup | Preparer Setup | Setup for roster preparer From IBMS | 4135 | 2023-05-21 | 2023-05-21 | 1 | 2023-05-22 | 2023-05-22 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Show the roster workflow | 4136 | 2023-05-23 | 2023-05-23 | 1 | 2023-05-28 | 2023-05-28 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Prepare pattern data | 4137 | 2023-05-29 | 2023-05-29 | 1 | 2023-05-30 | 2023-05-30 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration-Bulk(Backend) | 4138 | 2023-05-31 | 2023-05-31 | 1 | 2023-06-01 | 2023-06-01 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration | 4139 | 2023-06-03 | 2023-06-03 | 1 | 2023-06-06 | 2023-06-06 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Generate sample data for 1 month | 4140 | 2023-06-07 | 2023-06-07 | 1 | 2023-06-14 | 2023-06-14 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Front end validation with Click validate button and show error | 4141 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-18 | 2023-06-18 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Back end validation | 4142 | 2023-06-19 | 2023-06-19 | 1 | 2023-06-21 | 2023-06-21 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Submission of prepared roster | 4143 | 2023-06-22 | 2023-06-22 | 1 | 2023-06-26 | 2023-06-26 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | CRP | Dispatch Security Controller Application | Dispatch Security Controller Application | 3848 | 2023-01-10 | 2023-01-10 | 1 | 2023-01-10 | 2023-01-10 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | CRP | BMS for Approval | BMS for Approval | 3849 | 2023-01-11 | 2023-01-11 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Report | AIT Due in Credit Hold process | Show AIT due amount in CHR approval process | 4055 | 2023-05-14 | 2023-05-14 | 1 | 2023-05-21 | 2023-05-21 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | AIT Eligibility Setup | AIT Rule and % setup | Create New two field for AIT Rules in SOF form in sales Apps | 4056 | 2023-05-16 | 2023-05-16 | 1 | 2023-05-21 | 2023-05-21 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | AIT Eligibility Setup | AIT Rule and % setup | Create New two field for AIT Rules in SOF form in sales Apps ( Form customer order) | 4057 | 2023-05-18 | 2023-05-18 | 1 | 2023-05-21 | 2023-05-21 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | Query Setup | Query Setup | 4065 | 2023-02-01 | 2023-02-01 | 1 | 2023-02-15 | 2023-02-15 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | Temp Table Setup | Temp Table Setup for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4066 | 2023-02-15 | 2023-02-15 | 1 | 2023-03-01 | 2023-03-01 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | Package Setup | Package Setup for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4067 | 2023-03-01 | 2023-03-01 | 1 | 2023-03-15 | 2023-03-15 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | Console Application | Console Application for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4068 | 2023-03-15 | 2023-03-15 | 1 | 2023-04-01 | 2023-04-01 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | Scheduler | Scheduler for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4069 | 2023-04-01 | 2023-04-01 | 1 | 2023-04-15 | 2023-04-15 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | UAT SMS test | SMS test for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4070 | 2023-04-15 | 2023-04-15 | 1 | 2023-04-15 | 2023-04-15 | 1 | 17020000014499 | Huzefa Abbas Suratwala
SMS & Email fraud activities | SMS & Email fraud activities | BSRM Fraud Detection | UAT Email Test | Email Test for Money Receipt , Sales Order , Credit Memo , Debit Memo , Invoice , Challan | 4071 | 2023-04-15 | 2023-04-15 | 1 | 2023-04-30 | 2023-04-30 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Attn: Mr. Ashraf Kausar: Please develop AIT segregation system from invoice according to signed FDD | Keep track AIT enabled customer, Auto segregate and preserve AIT amount from invoice to make customer outstanding more accurate, Control MR application process considering AIT preserved amount, Revise all approval process related to customer outstanding, and finally provide a clear AIT outstanding report across the group | Application Procedure for AIT | Calculate AIT | Queue update validation check | 4045 | 2023-05-11 | 2023-05-11 | 1 | 2023-05-12 | 2023-05-12 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Admin Approval Workflow: Back end | Admin Approval Workflow: Back end | 3814 | 2022-12-19 | 2022-12-19 | 1 | 2022-12-26 | 2022-12-26 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Admin Approval Workflow:Font end | Admin Approval Workflow:Font end | 3815 | 2022-12-19 | 2022-12-19 | 1 | 2022-12-26 | 2022-12-26 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Admin Approval Workflow:HTML Report | Admin Approval Workflow:HTML Report | 3816 | 2022-12-19 | 2022-12-19 | 1 | 2022-12-26 | 2022-12-26 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Development | Dispatch Security Controller: Admin Approval | Dispatch Security Controller: Admin Approval | 3835 | 2022-12-20 | 2022-12-20 | 1 | 2022-12-26 | 2022-12-26 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Dear Sir,(Md. Mainul Hussain Khan) As proposed by Business, a Functional Design Document for QR Code Based Dispatch Security Controller app. Please next step for your end. Thank you | QR Code Based Dispatch Security Controller | Testing | BMS | BMS | 3840 | 2022-12-26 | 2022-12-26 | 1 | 2022-12-31 | 2022-12-31 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Security Updates | mobileapiold.bsrm.com/ReportQueryUI/ReportControllerandroid.aspx (Parametrizing all reports in this path) ( this report url is being used in BMS app , BMS web , OMR portal etc. ) | 3690 | 2022-12-09 | 2022-12-09 | 1 | 2022-12-12 | 2022-12-12 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Security Updates | Parameterizing GET requests OMR Transport Controller ( Dispactch Schedule Project ) | 3691 | 2022-12-13 | 2022-12-13 | 1 | 2022-12-16 | 2022-12-16 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Security Updates | ACCOUNT lock feature on OMR portal | 3692 | 2022-12-17 | 2022-12-17 | 1 | 2022-12-20 | 2022-12-20 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Security Updates | Remove AUTHORIZE controller on OMR ( as it was SECURITY risk ) | 3693 | 2022-12-21 | 2022-12-21 | 1 | 2022-12-24 | 2022-12-24 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Implement the security guideline in SalesEBS. | Implement the security guideline in SalesEBS. | Prevent Sql Injection | Security Updates | CORS implementation on OMR | 3694 | 2022-12-25 | 2022-12-25 | 1 | 2022-12-30 | 2022-12-30 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Update ui on sales ebs | 3632 | 2022-10-02 | 2022-10-03 | 0 | 2022-10-03 | 2022-10-03 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Commitment amount breakdown | 3633 | 2022-10-03 | 2022-10-03 | 1 | 2022-10-04 | 2022-10-04 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Creating / update DB tables | 3634 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-05 | 2022-10-05 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Updates in Credit Hold API | 3635 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-05 | 2022-10-05 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Updates in hris_do_pkg | 3636 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-05 | 2022-10-05 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Report | Updates in credit report | 3637 | 2022-10-05 | 2022-10-05 | 1 | 2022-10-06 | 2022-10-06 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Report | New Commitment report | 3638 | 2022-10-08 | 2022-10-08 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Create Setup | Status update scheduler | 3639 | 2022-10-09 | 2022-10-09 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | Credit Hold Commitment | Report | Updates in Credit hold history | 3640 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-12 | 2022-10-12 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Requesting to add below field in CHR Commitment Amount: Commitment Date : Comments : Tracking of payment as commitment: No. of commitment failure our of total Commitment. | Customer commitment management and follow-up against credit hold request. | UAT | UAT | UAT | 3641 | 2022-10-18 | 2022-10-18 | 1 | 2022-10-20 | 2022-10-20 | 1 | 17020000014499 | Huzefa Abbas Suratwala
Please implement Sales new Incentive structure in the system. | System driven sales incentive disbursement for core sales team and sales support team as per new policy. | Development of Sales Incentive with UI | Development of Sales Incentive with UI | Development of Sales Incentive with UI | 3328 | 2022-07-04 | 2022-07-04 | 1 | 2022-08-31 | NULL | 0 | 17020000014499 | Huzefa Abbas Suratwala

## Tonmoy & Saiful Haque
Project Title | Project Details | Milestone | Activity | Task | Task ID | Plan Start Date | Actual Start Date | Start On Time | Plan End Date | Actual End Date | Finish On Time | Assign Person HR ID | Assign Person Name
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | Source data analysis | Source data analysis | 3574 | 2022-10-23 | 2022-10-26 | 0 | 2022-10-23 | 2022-10-23 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | Architectural design | Architectural design | 3575 | 2022-10-24 | 2022-10-26 | 0 | 2022-10-25 | 2022-10-25 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | L2E-Middleware Database design and Execution | L2E-Middleware Database design and Execution | 3576 | 2022-10-26 | 2022-10-26 | 1 | 2022-10-27 | 2022-11-03 | 0 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Batch Creation and Status Upgradation | 3582 | 2022-11-20 | 2022-11-20 | 1 | 2022-11-20 | 2022-11-20 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Ingredient (IF+LRF+CCM) Lot identification and material transaction | 3583 | 2022-11-21 | 2022-11-21 | 1 | 2022-11-23 | 2022-11-23 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | (IF+LRF+CCM) step API | 3584 | 2022-11-24 | 2022-11-24 | 1 | 2022-11-24 | 2022-11-24 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Physical Inspection Step API | 3585 | 2022-11-27 | 2022-11-30 | 0 | 2022-11-27 | 2022-11-27 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Product, By-Product Lot creation and material transaction | 3586 | 2022-11-28 | 2022-11-30 | 0 | 2022-11-29 | 2022-11-29 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Activity (IF/LRF/CCM) planned and actual data insert API | 3587 | 2022-11-30 | 2022-11-30 | 1 | 2022-11-30 | 2022-11-30 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Resource (IF/LRF/CCM) planned and actual data insert/update API | 3588 | 2022-12-01 | 2022-11-30 | 1 | 2022-12-04 | 2022-12-04 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Sample creation API | 3589 | 2022-12-05 | 2022-12-05 | 1 | 2022-12-05 | 2022-12-05 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | ALL Chemistry data (IF/LRF/CCM) insert API | 3590 | 2022-12-06 | 2022-12-05 | 1 | 2022-12-07 | 2022-12-07 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Physical Inspection quality data entry API | 3591 | 2022-12-08 | 2022-12-07 | 1 | 2022-12-08 | 2022-12-08 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Quality Disposition API | 3592 | 2022-12-11 | 2022-12-12 | 0 | 2022-12-11 | 2022-12-11 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Activity/Step completion API | 3593 | 2022-12-12 | 2022-12-12 | 1 | 2022-12-12 | 2022-12-12 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process execution through L2E-Middleware | Batch completion and close API | 3594 | 2022-12-13 | 2022-12-12 | 1 | 2022-12-13 | 2022-12-13 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Package development | 3595 | 2022-12-14 | 2022-12-14 | 1 | 2022-12-15 | 2022-12-15 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Validation Check | 3596 | 2022-12-17 | 2022-12-19 | 0 | 2022-12-19 | 2022-12-19 | 1 | 17020000005213 | Syed Saiful Haque
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | eBS backend API process integration through L2E-Middleware | Process/Reprocess | 3597 | 2022-12-20 | 2022-12-19 | 1 | 2022-12-22 | 2022-12-22 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Mapping Pay item and Percentage logic | 3616 | 2022-09-24 | 2022-09-24 | 1 | 2022-09-26 | 2022-09-26 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Create new evaluation with updated event reason | 3617 | 2022-09-26 | 2022-09-26 | 1 | 2022-09-29 | 2022-09-29 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | Payroll process and Check | 3618 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-01 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | Payroll Process | PF and Oracle Invoice process | 3619 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-01 | 2022-10-01 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Create Company & DB | 3621 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-03 | 2022-10-03 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Journal and voucher setup | 3622 | 2022-10-03 | 2022-10-03 | 1 | 2022-10-04 | 2022-10-04 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Ledger setup | 3623 | 2022-10-04 | 2022-10-04 | 1 | 2022-10-05 | 2022-10-05 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in SF integration procedure | 3624 | 2022-10-05 | 2022-10-05 | 1 | 2022-10-06 | 2022-10-06 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in iBMS HRIS Employee Form | 3625 | 2022-10-08 | 2022-10-08 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Create Setup | Change in iBMS HRIS Voucher Forms | 3626 | 2022-10-09 | 2022-10-09 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Data Preparation | Opening data upload | 3627 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-12 | 2022-10-12 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Data Preparation | Create payitems and company mapping | 3628 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-11 | 2022-10-11 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Report | Employeewise WPPF Report | 3629 | 2022-10-12 | 2022-10-12 | 1 | 2022-10-13 | 2022-10-13 | 1 | 17020000005213 | Syed Saiful Haque
Please provide a system to calculate WPPF amount and amount to be shifted to tax file. | Change request on WPPF management integrated with HRIS and tax certificate generation. | WPPF Accounting System | Report | Change Accounting report for WPPF | 3630 | 2022-10-13 | 2022-10-13 | 1 | 2022-10-16 | 2022-10-16 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Create Setup | Create Table | 3650 | 2022-09-02 | 2022-09-02 | 1 | 2022-09-02 | 2022-09-02 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Create Setup | Create SQL Jobs | 3651 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Architecture | Create .NET Core project for CM | 3652 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Monthly Tax Summary | Process and Query Preparation | 3493 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-14 | 2022-09-14 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report 108 | Process and Query Preparation | 3496 | 2022-10-03 | 2022-10-03 | 1 | 2022-10-04 | 2022-10-04 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Report Perquisite | Process and Query Preparation | 3499 | 2022-10-06 | 2022-10-06 | 1 | 2022-10-06 | 2022-10-06 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | Tax Deduction Summary | Process and Query Preparation | 3502 | 2022-10-10 | 2022-10-10 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Report | WPPF Individual Tax Confirmation | Process and Query Preparation | 3505 | 2022-10-13 | 2022-10-06 | 1 | 2022-10-13 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | Generate Challan WPPF | Generate Challan | Generate Challan | 3208 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-20 | 2022-09-19 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | Upload acknowledge of return by user | Upload acknowledge of return by user | 3222 | 2022-10-19 | 2022-10-16 | 1 | 2022-10-19 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Dear Saiful bhai, as per verbal instruction of Shekhar sir & attached CRAF, please develop a system of automated income tax calculation system with certificate and system generated challan. | Automated income tax calculation system with certificate and system generated challan | UI | View uploaded acknowledement by HR and Accounts | View uploaded acknowledement by HR and Accounts | 3223 | 2022-10-19 | 2022-10-06 | 1 | 2022-10-19 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | CPI | Create iFlow in CPI | 3614 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-18 | 2022-09-18 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Implemenation | Integrate in Tax Certificate Project | 3654 | 2022-09-03 | 2022-09-03 | 1 | 2022-09-24 | 2022-09-24 | 1 | 17020000005213 | Syed Saiful Haque
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Implemenation | Integrate in Kolkata Attendance Process | 3655 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Policy Implementation | Create shift as per policy | 3658 | 2022-10-11 | 2022-10-11 | 1 | 2022-10-13 | 2022-10-13 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Policy Implementation | Attendace data configuration as per policy | 3659 | 2022-10-16 | 2022-10-16 | 1 | 2022-10-18 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | Configuration in Attendance DB | 3660 | 2022-10-18 | 2022-10-18 | 1 | 2022-10-18 | 2022-10-18 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | TimeZone change in Lead Management API | 3661 | 2022-10-19 | 2022-10-19 | 1 | 2022-10-19 | 2022-10-19 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | File Upload option in HRIS | 3662 | 2022-10-20 | 2022-10-20 | 1 | 2022-10-20 | 2022-10-20 | 1 | 17020000005213 | Syed Saiful Haque
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Kolkata Attendance Process | Attendance Process | Process data in HRIS | 3663 | 2022-10-21 | 2022-10-21 | 1 | 2022-10-22 | 2022-10-22 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Create Company & DB | 3994 | 2023-03-01 | 2023-03-01 | 1 | 2023-03-04 | 2023-03-04 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Journal Voucher &Ledger Setup | 3995 | 2023-03-04 | 2023-03-04 | 1 | 2023-03-10 | 2023-03-10 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Create Setup | Change in SF integration procedure Change in iBMS HRIS EmployeeForm Change in iBMS HRIS Voucher Forms | 3996 | 2023-03-11 | 2023-03-11 | 1 | 2023-03-14 | 2023-03-14 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Claim Form | 3997 | 2023-03-15 | 2023-03-15 | 1 | 2023-03-23 | 2023-03-23 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Claim to Voucher by Data Load | 3998 | 2023-03-25 | 2023-03-25 | 1 | 2023-03-27 | 2023-03-27 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Transaction | Opening data upload | 3999 | 2023-03-27 | 2023-03-27 | 1 | 2023-03-30 | 2023-03-30 | 1 | 17020000005213 | Syed Saiful Haque
Implement the WWF system. | Accounting management for welfare fund and claim tracking and disbursement including employee wise ledger statement | WWF Accounting System | Report | Summary & Details Report | 4000 | 2023-04-02 | 2023-04-02 | 1 | 2023-04-04 | 2023-04-04 | 1 | 17020000005213 | Syed Saiful Haque
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | Prepare ERD | 4131 | 2023-05-10 | 2023-05-10 | 1 | 2023-05-11 | 2023-05-11 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | Database | New DB Object | 4132 | 2023-05-14 | 2023-05-14 | 1 | 2023-05-15 | 2023-05-15 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | API | Create API Structure with CQRS Pattern | 4133 | 2023-05-16 | 2023-05-16 | 1 | 2023-05-17 | 2023-05-17 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | System design | UI | Angular Project setup + Login | 4134 | 2023-05-18 | 2023-05-18 | 1 | 2023-05-20 | 2023-05-20 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Authorization Setup | Preparer Setup | Setup for roster preparer From IBMS | 4135 | 2023-05-21 | 2023-05-21 | 1 | 2023-05-22 | 2023-05-22 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Show the roster workflow | 4136 | 2023-05-23 | 2023-05-23 | 1 | 2023-05-28 | 2023-05-28 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Prepare pattern data | 4137 | 2023-05-29 | 2023-05-29 | 1 | 2023-05-30 | 2023-05-30 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration-Bulk(Backend) | 4138 | 2023-05-31 | 2023-05-31 | 1 | 2023-06-01 | 2023-06-01 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Employee wise roster pattern configuration | 4139 | 2023-06-03 | 2023-06-03 | 1 | 2023-06-06 | 2023-06-06 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Generate sample data for 1 month | 4140 | 2023-06-07 | 2023-06-07 | 1 | 2023-06-14 | 2023-06-14 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Front end validation with Click validate button and show error | 4141 | 2023-06-15 | 2023-06-15 | 1 | 2023-06-18 | 2023-06-18 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Back end validation | 4142 | 2023-06-19 | 2023-06-19 | 1 | 2023-06-21 | 2023-06-21 | 1 | 17020000014498 | Tonmoy Rudra
Attn Kausar Bhai, Please incorporate newly discussed and decided rostering and OT . | Roster and overtime requisition/amendment by department with correspondent approval along with auto shift management lead to automated attendance process. | Roster initiation | Roster Preparation | Submission of prepared roster | 4143 | 2023-06-22 | 2023-06-22 | 1 | 2023-06-26 | 2023-06-26 | 1 | 17020000014498 | Tonmoy Rudra
Software support required so Kolkata office punching data can directly transferred to hris/sucessfactor as per indian timing schedule | Attendance data processing and integration with HRIS for Kolkata office according to their time-zone. | Concurrent Manager Desktop | Concurrent Manager Project | Create Concurrent for CSV File Upload | 3657 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop a system to integrate Success Factors(SF) payroll. | Change request on payroll integration with Success Factors(SF) | Integration SF to Payroll | API | Create API to receive payroll data | 3615 | 2022-09-19 | 2022-09-19 | 1 | 2022-09-22 | 2022-09-22 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Report | PMGM | For Year end appraisal we need a report contains various rating. Sharing the format for your easy understanding. [Ticket NO: 133023] | 3329 | 2022-07-07 | 2022-07-07 | 1 | 2022-07-13 | 2022-07-13 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We have found error message when testing new goal plan 22-23 in the production system. Need to raise ticket to SAP. Please support us in this issue.. Ticket Details [Ticket NO: 136980] | 3510 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | PMGM | We need to update some features in the existing performance form (incorporate comments in +1 Manager, sign-off step) which was observed last year & discussed with you. Please support us in doing this in the system to start the new goal plan 22-23. Thank you Ticket Details [Ticket NO: 137115] | 3511 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-30 | 2022-09-30 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | As discussed, please upload bulk employees for proxy management. Ticket Details [Ticket NO: 139489] | 3571 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
Dear Sumon and Tonmoy, As discussed, please generate some dynamic reports like employee info, leave info, etc. | SAP Success factor Configuration Change, Other Support and Report | Configuration Change | EC | Add Proxy for HR person | 3572 | 2022-10-02 | 2022-10-02 | 1 | 2022-10-02 | 2022-10-02 | 1 | 17020000014498 | Tonmoy Rudra
Please develop a concurrent manager for newly assigned systems. | Central concurrent manager to manage request queue in background for in-house application. | Concurrent Manager | Develop | Develop classed to process CSV files | 3653 | 2022-10-01 | 2022-10-01 | 1 | 2022-10-10 | 2022-10-10 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | UI Design and Development | 3598 | 2022-12-26 | 2022-12-26 | 1 | 2023-01-02 | 2023-01-02 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Physical Inspection | 3599 | 2023-01-03 | 2023-01-03 | 1 | 2023-01-15 | 2023-01-15 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch details | 3600 | 2023-01-16 | 2023-01-16 | 1 | 2023-01-22 | 2023-01-22 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Batch correction | 3601 | 2023-01-23 | 2023-01-23 | 1 | 2023-01-30 | 2023-01-30 | 1 | 17020000014498 | Tonmoy Rudra
MIDDLEWARE DEVELOPMENT FOR BSRM STEELS (MELTING-2) | Middleware development for BSRM Steels (MELTING-2) integrated with oracle eBS | System Development | UI Design and Development | Formula item configuration and modification | 3602 | 2023-01-31 | 2023-01-31 | 1 | 2023-02-02 | 2023-02-02 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Group Setup, Param Setup | 2596 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item type setup | 2597 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Item Ratio Setup | 2598 | 2022-09-13 | 2022-09-13 | 1 | 2022-09-15 | 2022-09-15 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Org Setup | Company Setup | 2599 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Setup | User and workflow and cost center and location setup, ADD Edit And delete | 2600 | 2022-08-10 | 2022-08-10 | 1 | 2022-08-12 | 2022-08-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | User Permissions Setup | Permission on ORG, Region, Common Budget, | 2601 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-14 | 2022-08-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Nature Of Accounts Setup | Common budget NoA setup, | 2603 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-17 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | PBCPM(Planing Budget….) Common Budget Setup | Common budget NoA setup, | 2605 | 2022-08-21 | 2022-08-21 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget Setup | Sales Budget Setup with Region. | Region wise setup. | 2606 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Draft Mode Save | Draft mode save from file and UI. | 2609 | 2022-07-03 | 2022-07-03 | 1 | 2022-07-04 | 2022-07-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2610 | 2022-08-17 | 2022-08-17 | 1 | 2022-08-21 | 2022-08-21 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Submit Budget | Submit budget with validation and save | 2611 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-23 | 2022-08-23 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Multi layer approval | 2612 | 2022-08-22 | 2022-08-22 | 1 | 2022-08-25 | 2022-08-25 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | PBCPM Comments entry | 2613 | 2022-08-23 | 2022-08-02 | 1 | 2022-08-24 | 2022-08-24 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Notification Mail | 2614 | 2022-08-25 | 2022-08-25 | 1 | 2022-08-27 | 2022-08-27 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Expense and Overhead Budget | Work Flow | Work flow Stage visibility | 2615 | 2022-08-28 | 2022-08-28 | 1 | 2022-08-28 | 2022-08-28 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Draft Mode Save | Draft mode save from file and UI. | 2616 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2617 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-30 | 2022-08-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Submit Budget | Submit budget with validation and save | 2618 | 2022-08-30 | 2022-08-30 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Multi layer approval | 2619 | 2022-08-31 | 2022-08-31 | 1 | 2022-08-31 | 2022-08-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | PBCPM Comments entry | 2620 | 2022-09-01 | 2022-09-01 | 1 | 2022-09-01 | 2022-09-01 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Notification Mail | 2621 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-04 | 2022-09-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Production Budget | Work Flow | Work flow Stage visibility | 2622 | 2022-09-04 | 2022-09-04 | 1 | 2022-09-05 | 2022-09-05 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | File template management | File template Upload as per NoA assignment | 2624 | 2022-09-06 | 2022-09-06 | 1 | 2022-09-06 | 2022-09-06 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Draft Mode Save | Draft mode save from file and UI. | 2625 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2626 | 2022-09-07 | 2022-09-07 | 1 | 2022-09-07 | 2022-09-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Submit Budget | Submit budget with validation and save | 2627 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Multi layer approval | 2628 | 2022-09-11 | 2022-09-11 | 1 | 2022-09-11 | 2022-09-11 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | PBCPM Comments entry | 2629 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Notification Mail | 2630 | 2022-09-12 | 2022-09-12 | 1 | 2022-09-12 | 2022-09-12 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Raw Packing Consumable Consumption Budget | Work Flow | Work flow Stage visibility | 2631 | 2022-09-12 | 2022-09-11 | 1 | 2022-09-13 | 2022-09-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template download as per NoA assignment | 2632 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | File template management | File template Upload as per NoA assignment | 2633 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Draft Mode Save | Draft mode save from file and UI. | 2634 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2635 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Submit Budget | Submit budget with validation and save | 2636 | 2022-08-04 | 2022-08-04 | 1 | 2022-08-04 | 2022-08-04 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Multi layer approval | 2637 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | PBCPM Comments entry | 2638 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Notification Mail | 2639 | 2022-08-07 | 2022-08-07 | 1 | 2022-08-07 | 2022-08-07 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Store and Spare Budget | Work Flow | Work flow Stage visibility | 2640 | 2022-08-08 | 2022-08-08 | 1 | 2022-08-08 | 2022-08-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template download as per NoA assignment | 2650 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | File template management | File template Upload as per NoA assignment | 2651 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Draft Mode Save | Draft mode save from file and UI. | 2652 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2653 | 2022-08-13 | 2022-08-13 | 1 | 2022-08-13 | 2022-08-13 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Submit Budget | Submit budget with validation and save | 2654 | 2022-08-14 | 2022-08-14 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Multi layer approval | 2655 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | PBCPM Comments entry | 2656 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Notification Mail | 2657 | 2022-08-16 | 2022-08-16 | 1 | 2022-08-16 | 2022-08-16 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Common Budget | Work Flow | Work flow Stage visibility | 2658 | 2022-08-29 | 2022-08-29 | 1 | 2022-08-29 | 2022-08-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template download as per NoA assignment | 2659 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management | File template Upload as per NoA assignment | 2660 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Draft Mode Save | Draft mode save from file and UI. | 2661 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Actual Budget check | Show Previous Actual budget pop up by Click a button | 2662 | 2022-10-29 | 2022-10-29 | 1 | 2022-10-29 | 2022-10-29 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Submit Budget | Submit budget with validation and save | 2663 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Multi layer approval | 2664 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | PBCPM Comments entry | 2665 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Notification Mail | 2666 | 2022-10-30 | 2022-10-30 | 1 | 2022-10-30 | 2022-10-30 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template download as per submitted capital budget | 2667 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | File template management PBCPM NoA | File template Upload as per submitted capital budget. | 2668 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Capital Budget | Work Flow | Work flow Stage visibility | 2669 | 2022-10-31 | 2022-10-31 | 1 | 2022-10-31 | 2022-10-31 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Review for previous process | Transfar previous reviews data to half yearly review. | 2673 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-08 | 2022-09-08 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Open Budget period | Budget setup activty by PBCPM | 2674 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Half yearly review, | Actual consumption for current year. | Pop View for actual consumption | 2675 | 2022-09-08 | 2022-09-08 | 1 | 2022-09-10 | 2022-09-10 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Access wise query preparation. | 2681 | 2022-09-14 | 2022-09-14 | 1 | 2022-09-14 | 2022-09-14 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget view API | 2682 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | Budget View | Budget View | Budget View UI | 2683 | 2022-08-03 | 2022-08-03 | 1 | 2022-08-03 | 2022-08-03 | 1 | 17020000014498 | Tonmoy Rudra
Please develop e-budgeting system for FY 2022-2023 | Develop e-budgeting system for FY 2022-2023 | UAT | UAT | UAT | 2690 | 2022-11-08 | NULL | 0 | 2022-11-10 | NULL | 0 | 17020000014498 | Tonmoy Rudra